## EML_Tool_WP
Compliance zu WPs CDLEML |  | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | Start Date | Est. End Date | Weight [1,5] | Progress | Description | Status | Responsible | Student | Tasks | State | Deliverable ID | Deliverable Goal | Deliverable Type | Deliverable Content | Links | Priority
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  |  |  | %
[11 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
| Milestones | [9 empty] | 2020 5 8: M1.1; 2020 9 12: M2.1; 2020 11 14: M1.2; 2021 3 18: M2.2; 2021 9 24: M1.3M2.3
Deliverables
WP1.1 | Create estimations for lat, throughput, power, energy, acc, resources | [39 empty] | 51.11% | Anforderung: Modelle für 4 Platformen | Meilenstein 1.1 geschafft. Throughput nicht wichtig->auslassen | bar: 2019 10 1 to 2021 3 18
WP1.1.1 | State of the Art Latency und Power Estimation Modelle aufsetzen | [36 empty] | 2020-09-01 | 2020-10-30 |  | 100% | Setup Neural Power latency and power estimation model | Finished | MWU |  |  | completed | D1.1.1 | Baseline for own estimators | Publication | * included in the publication of ANNETTE
| Neural Power aufsetzen mit Modell von NCS2 | [38 empty] | 2 | 100% | Modell implementieren in beliebiger Umgebung; NeuralPower übertragbar machen (andere Umgebung?); Estimatorschnittstelle implementieren; ein Modell trainieren (Xavier, NCS2…) Demonstration der Latenzabschätzung eines Netzes; Output: Latenz | -Aufgabe wird aufgelassen, weil die Ergebnisse nicht gut sind. Schlussfolgerung: Unsere Methoden sind besser | MWU |  | [x] NCS2 messdaten modellieren [-] Xilinxdaten modellieren [-] Graphikkarte Siemensserver modellieren [-] Manual schreiben [-] Am Server aufsetzen | bar: 2020 9 12 to 2020 10 13
WP1.1.2 | Estimator Blackthorn for Latency (NVIDIA) | [36 empty] | 2019-10-01 | 2021-02-28 |  | 81.11% | Model based latency estimator method | Wie weit seid ihr? Wollen wir alle diese Plattformen machen? | ML | ML |  | active | D1.1.2 | Estimation model for Embedded (Nvidia) Platforms | Repository, Publication | * Publication * Benchmarking Results and Estimation Models for NVIDIA * Repository on Github (Open source) |  | 1
| Martins latency estimator mit Modell von Xavier erstellen | [38 empty] | 2 | 50% |  | *Modellstruktur fertig. Übertragung auf Xavier, Messungen | ML |  | [] Messen [] Modell erstellen [] Modell übertragen | bar: 2020 12 15
| Martins latency estimator mit Modell von Nano erstellen | [38 empty] | 5 | 90% | Modell implementieren in beliebiger Umgebung; NeuralPower übertragbar machen (andere Umgebung?); Estimatorschnittstelle implementieren; ein Modell trainieren (Xavier, NCS2…) Demonstration der Latenzabschätzung eines Netzes; | *3 Layertypen fehlen | ML |  | [] 3 Layertypen neu hinzufügen, Depth Separable Convolutions +2 [] Code aufräumen 10.12.2020 [] In Repository stellen | bar: 2020 9 12 to 2020 12 15
| Martins latency estimator mit Modell von TX2 erstellen | [38 empty] | 2 | 90% | Modell implementieren in beliebiger Umgebung; NeuralPower übertragbar machen (andere Umgebung?); Estimatorschnittstelle implementieren; ein Modell trainieren (Xavier, NCS2…) Demonstration der Latenzabschätzung eines Netzes; | *3 Layertypen fehlen | ML |  | [] 3 Layertypen neu hinzufügen [] Code aufräumen | bar: 2020 9 12 to 2020 12 15
WP1.1.3 | Estimator method ANETTE for Latency (Intel, ARM, Xilinx) | [36 empty] | 2019-10-01 | 2021-02-28 |  | 54% | Statistic and model based latency estimator method | Wie weit bis du da? | MW | MW |  | active | D1.1.3 | Estimator method ANETTE for Latency (Intel, ARM, Xilinx) | Repository, Publication | * Publication of ANNETTE * Benchmark Results of NCS2 Platform * Benchmark Results of Xilinx Platform * Benchmark Results of ARMNN Example Platform * Prediction Models for all three platforms * Open Source Repository for Latency Estimation |  | 1
| Latency Intel: ANETTE aufsetzen mit Modell von NUC erstellen | [38 empty] | 3 | 30% |  |  | MW | bar: 2021 1 16
| Latency Xilinx: ANETTE aufsetzen mit Modell von Xilinx ZCU102 + spezielle IP erstellen | [38 empty] | 5 | 80% |  | Modell fertig, Schnittstelle nach außen offen | MW |  | [] Schnittstelle erstellen, code cleaning | bar: 2020 9 12 to 2020 12 15
| Latency Xilinx: ANETTE aufsetzen mit Modell von Xilinx mit Ausbaustufen der IP erweitern | [38 empty] | 0 |  |  | Nicht so wichtig. Ein Xilinx reicht im Moment
| Latency Intel: ANETTE latency mit Modell von NCS2 erstellen | [38 empty] | 4 | 80% | Modell implementieren in beliebiger Umgebung; NeuralPower übertragbar machen (andere Umgebung?); Estimatorschnittstelle implementieren; ein Modell trainieren (Xavier, NCS2…) Demonstration der Latenzabschätzung eines Netzes; Size 1, sync modus | Fertig für sync modus, size 1. Schnittstelle nach außen offen | MW |  | [] Schnittstelle erstellen, code cleaning | bar: 2020 9 12 to 2020 12 15
| Latency ARM: ANETTE auf Raspberry PI aufsetzen | [38 empty] | 3 | 0% |  |  | MW | bar: 2021 1 16 to 2021 3 18
WP1.1.4 | Estimation of Power through a White box model | [36 empty] | 2020-08-01 | 2020-10-30 |  | 20% | Power estimation through circuit simulator | Cancelled in ist current idea | CK |  |  | paused | [5 empty] | 3
| Power Xilinx: Generelle Powerabschätzungsmodell durch Synthetisierung erstellen | [38 empty] | 5 | 20% | Mit Powerschätzungen erweitern. Systematisch Xilinx und Sticks durchmessen. CK: FPGA feingranulare Abschätzung der Energie. Xilinx Power Estimator, geplant technologieunabhängig, auf alle FPGAs. Technologielibrary. Kommersielle Lösungen gibt es schon | - Testbeispiel gefunden und implementieren - Testsetup machen, wie misst man | CK |  | [] Besprechung mit Herbert @MW [] HW bestellen [] Studentenarbeit ausschreiben [] Mit Multimeter oder DAQ Messung | bar: 2020 9 12 to 2020 12 15
WP1.1.5 | Estimation of Power through ANETTE | [39 empty] | 0% | Power estimation through the estimator ANNETTE |  | MW |  |  | open | [5 empty] | 2
| Power Xilinx: Powerschätzung von ANETTE auf Xilinx erweitern? | [38 empty] | 0 | 0%
| Power ARM: Powerestimation Raspberry PI | [38 empty] | 3 | 0% | ANETTE auf Raspberry PI erweitern. Studentenarbeit dafür verwenden | Nicht gestartet | MW
WP1.1.6 | Estimation of On-Chip Resources | [39 empty] | 0% | Estimate resources like memory usage |  | ML |  |  | open | [5 empty] | 3
| Resourcenestimierung NVIDIA Möglichkeiten sondieren | [38 empty] | 2 | 0% | Seminararbeit für Literatursuche. Praktische Studentenarbeit für die Ausführung. Untersuchung Memoryusage, Bandwidth, Verkehr zwischen Prozessor und DRAM. Wie kann das Ressourcenprofil ändern durch Parameterisierung. NVIDIA-Plattformen. nSight verwenden. Frage: Welches Netz würde für eine bestimmte HW die Resourcen maximal ausnutzen? | Nicht gestartet | ML |  | [] Studentenarbeit ausschreiben [] Platform mit den besten Tools auswählen | bar: 2020 10 13 to 2021 4 19
WP1.2 | Optimize HW Dependent Settings | [39 empty] | 38.97% | Anforderung: HW Optimizations für 4 Plattformen | *NVIDIA Nano und welche noch? NCS2 wäre naheliegend. Meilenstein 1.2 50% geschafft | bar: 2020 4 7 to 2021 6 21
WP1.2.1 | NVIDIA Profiling | [36 empty] | 2020-03-01 | 2021-03-31 |  | 35.56% | HW settings profiling of NVIDIA Xavier, Jetson Nano (Bachelor thesis) and TX2 |  | SH | SH |  | active | D1.2.1 | Latency, power and energy profiling of HW options of NVIDIA Jetson Nano, Xavier, TX2 | Bachelor thesis, Publication, Documentation | * Power measurements * Batchsizes 1-4 * Variation of possible HW options e.g. GPU frequency * Analysis of power peaks and settings definition to prevent overheating |  | 1
| NVIDIA Jetson Nano Hardware Profiling durchführen | [38 empty] | 4 | 80% | Im synchronen Modus nur. Im async geht das nicht. Zusatzmessungen Jetson Nano - Batchsize 1-4, weil sie mit einem Netz mehrere Sensorinputs gleichzeitig anschauen, Synchronbilder - Powerminimierung bzw. Powerkontrolle, weil es bei Nano öfters passiert ist, dass der 100W Netzteil überlastet wird und das Gerät thermisch eingeht. Stresstests wären hier interessant für die Geräte bzw. wie man so einen Zustand vermeiden kann. | *Bakarbeit fast fertig. * Zusatzmessungen von ME offen | SH |  | [] Bericht mit notwendigen Messungen drinnen (Bakarbeit + Zusatzmessungen) | bar: 2020 9 12; 2020 11 14 to 2020 12 15
| NVIDIA Jetson Nano Hardware Optimierung Implementierung auf Nano | [38 empty] | 1 | 0% | Scripts implementieren, wo man Einstellungen für min Latency, min Power oder min Energy einstellen kann |  | SH | bar: 2020 11 14 to 2020 12 15
| NVIDIA TX2 Hardware Profiling durchführen | [38 empty] | 2 | 0% | Dieselbe Messungen wir bei Nano | Nicht gestartet | SH | bar: 2021 1 16 to 2021 2 17
| NVIDIA Xavier Hardware Profiling durchführen | [38 empty] | 2 | 0% | Dieselbe Messungen wir bei Nano | Nicht gestartet | SH | bar: 2021 3 18
WP1.2.2 | ARM Profiling | [36 empty] | 2020-11-01 | 2021-02-28 |  | 46% | HW settings profiling of Raspberry Pi |  | MI |  |  | active | D1.2.2 | Evaluation of an ARM CPU | Repository, Document | * Guide how to setup ArmNN and TFLite for 32 and 64 bit of a Raspberry Pi 4 (32/64 Bit) * Software projectwith benchmarks, test, conversion, inferenz*Scripts for ArmNN * Table with latency comparison of ArmNN and TFLite 32/64 Bit with inference with an ordinary accelerator |  | 1
| ARM (Raspberry) HW Optimierungen untersuchen | [38 empty] | 4 | 50% | Settings für CPU -> Latenz, Power und Energy |  | MI | bar: 2020 10 13
| ARM HW Optimierungen als Script implementieren | [38 empty] | 1 | 30% |  |  | MI
WP1.2.3 | Xilinx Profiling | [36 empty] | 2020-11-01 |  |  | 6.667% | HW settings profiling of Xilinx ZCU102 |  | MWU |  |  | active | D1.2.3 |  | Document | * Analysis how many needed kernels, share of FPGA used, consequences of consumes power, tradeoff between speedup and power * Repository * Inference possible |  | 1
| Xilinx HW Optimerungensoptionen untersuchen | [38 empty] | 2 | 20% | Größe systosischen Array, Puffer, DSP untersuchen |  | MWU
| Xilinx HW Optimierungen als Script implementieren | [38 empty] | 4 | 0% |  |  | MWU
WP1.2.4 | Intel Profiling | [36 empty] | 2019-10-01 | 2020-03-31 |  | 60% | HW settings profiling of Intel NCS2 and CPU through OpenVino |  | MI |  |  | active | D1.2.4 |  | Document, thesis | * Evaluation of stick sync vs. async mode and other settings of NCS2 as part of thesis MW * Results included in ANNETTE D1.1.3 |  | 3
| OpenVino CPU Hardwareoptimierung untersuchen | [38 empty] | 4 | 10% | Unterschied GPU/CPU am NUC Performace, Auslastung der Cores. | Bachelorarbeit ausschreiben für Latenz und Power und Energiemessungen? | AW
| OpenVino Hardwareoptimierung Implementierung von Scripts auf NUC and NCS2 | [38 empty] | 1 | 100% | Scripts implementieren, wo man Einstellungen für min Latency, min Power oder min Energy einstellen kann
| NCS2 Hardwareoptimierungsoptionen untersuchen | [38 empty] | 4 | 100% | Settings für min Latenz, Power und Energy. Modus max. power how to use. Possiblity for syncronous inference without preprocessing. NCS2 limited through USB connector. Sync vs. asyncronous mode. Recommendation from Intel |  | MI | bar: 2020 9 12 to 2020 10 13
WP1.3 | Map Models of hardware | [39 empty] | 30.09% | Anforderung: Optimierungsstruktur für 4 Plattformen | bar: 2021 1 16 to 2021 9 24
WP1.3.1 | Gemeinsame Infrastruktur Hardwareschnittstelle | [39 empty] | 15% | Common software interfaces for devices |  | MWU |  |  | open | [5 empty] | 3
| EML-Process: Gemeinsame Estimatorschnittstelle aus Inferenzschnittstelle erstellen | [38 empty] | 2 | 30% | Das Inferenzinterface erweitern (extends) für notwendige Inputs für die Estimators; Welche Files wo in welches Format abgelegt werden, um vom Programm gefunden zu werden; Ort und Formats des Reports festlegen. WICHTIG: Diese Schnittstelle soll gleich sein wie die Schnittstelle zur echten HW | - Parser von Matthias Format vorhanden - Master: Datensatz in Matthias Format | Marco |  | [] Inputformate von Martin interpretieren [] Klären wie wir jobs nicht parallel ausführen (eventuell ohne Taskspooler) | bar: 2020 7 10 to 2020 8 11; 2020 10 13 to 2020 11 14
| EML-Process: Startscript/Pythonschnittstelle für Inferenz an Hardwareumgebungen erstellen | [38 empty] | 2 | 0% | Standardisierte Scripts für das Ausführen der Inferenz schreiben: Inferenz mit Bericht erhalten, definieren wo es abgelegt werden soll, welches Format. |  | Marco |  | [] Infos und Scripts von Matthias und Matvey bekomme [] Matvey NUC Openvino installieren | bar: 2020 11 14
WP1.3.2 | Inferenz an NVIDIA Hardware ermöglichen | [36 empty] | 2020-03-01 | 2020-03-31 |  | 12.5% | Inference on Nano, TX2 and Xavier |  | AM |  |  | active | D1.3.2 | Inference NVIDIA: Out of the box inference with defined networks with or without tensor-rt | Document, repository | * 1x Obj. Detection, 1x segmentation * Inference with tensor-rt: YoloV4 (Bck YoloV3), DeepLabV3, SSD-MobileNetV2, Object Detection API 2.0 * Guides in Github on how to setup the devices * Nano, TX2, Xavier environment completed |  | 1
| Inferenz NVIDIA: Inferenzmodul für alle NVIDIA Geräte erstellen für Latenz, Accuracy und Throughput und Timings erstellen | [38 empty] | 4 | 20% | Es soll Pytorch und TF ausführen können, Bericht im richtigen Format zurückgeben, wenn Daten und Modell bekannt sind. Gesammelt soll Netzlatenz, Layer und total, Throughput, Accuary oder IoU wenn Bilder verwendet werden, Zeit fürs Laden der Inferenzdaten, Gesamtinferenzzeit | Priorität! | AM | bar: 2020 10 13 to 2020 11 14
| Inferenz NVIDIA: Inferenzmodul für Xavier aufsetzen mit Pytorch und TF 2.3 | [38 empty] | 1 | 20% | Images herunterladen und aufsetzen, TF und Pytorch letzte Versionen. Inferenzmodul mit Bericht notwendig | Priorität! *Dockerimages noch offen *OpenCV auf Xavier | AM |  | [] Tests der Images [x] Xavier am Router hängen [] TF2-Saved_Model + h5-Modelle zu tensorrt konvertieren [] Inferenz mit tensorrt und Bilder | bar: 2020 10 13 to 2020 11 14
| Inferenz NVIDIA: Inferenzmodul für TX2 aufsetzen mit Pytorch und TF 2.3 | [38 empty] | 1 | 0% | Images herunterladen und aufsetzen, TF und Pytorch letzte Versionen. Inferenzmodul mit Bericht notwendig | Priorität! | AM | bar: 2020 11 14
| Inferenz NVIDIA: Inferenzmodul für Nano aufsetzen mit Pytorch und TF 2.3 | [38 empty] | 1 | 0% | Images herunterladen und aufsetzen, TF und Pytorch letzte Versionen. Inferenzmodul mit Bericht notwendig | Priorität! | AM | bar: 2020 11 14
| Inferenz NVIDIA: Standardisierte Startscripts für NVIDIA Containers/Umgebungen erstellen | [38 empty] | 1 | 0% | Standardisierte Scripts für das Ausführen der Inferenz schreiben: Inferenz mit Bericht erhalten, definieren wo es abgelegt werden soll, welches Format |  | AM |  | [] Dockerscript erstellen | bar: 2020 10 13 to 2020 11 14
WP1.3.3 | Inferenz an Intelgeräte ermöglichen | [36 empty] | 2019-10-01 | 2021-01-31 |  | 91.25% | Inference on NUC and NCS2 |  | MI |  |  | active | D1.3.3 | Inference Intel: Out of the box inference with defined networks with or without OpenVino | Document, repository | * 1x Obj. Detection, 1x segmentation * Inference with OpenVino: YoloV4 (Bck YoloV3), DeepLabV3, optional Object Detection API 2.0 SSD-MobileNetV2 * Guides in Github on how to setup the devices * NUC, NCS2 environment completed |  | 2
| Inferenz Intel: Inferenzmodul für alle OpenVinogeräte erstellen | [38 empty] | 4 | 100% | Es soll Pytorch und TF ausführen können, Bericht im richtigen Format zurückgeben, wenn Daten und Modell bekannt sind. Gesammelt soll Netzlatenz, Layer und total, Throughput, Accuary oder IoU wenn Bilder verwendet werden, Zeit fürs Laden der Inferenzdaten, Gesamtinferenzzeit | Deeplab, ResNet geht | MW | bar: 2020 10 13 to 2020 12 15
| Inferenz Intel: Inferenzstart Script für Openvino erstellen | [38 empty] | 1 | 30% |  | Priorität! | AW |  | [] Mit einem Netz testen | bar: 2020 10 13
| Inferenz Intel: Dockerimages/Umgebungen für Intel NUC aufsetzen mit Pytorch und TF 2.3 | [38 empty] | 3 | 100% | Images herunterladen und aufsetzen, TF und Pytorch letzte Versionen. Inferenzmodul mit Bericht notwendig |  | MW | bar: 2020 10 13
WP1.3.4 | Inferenz an ARM ermöglichen | [36 empty] | 2020-10-01 | 2021-02-28 |  | 10% | Inference on Raspberry Pi | Welche Hardware noch wollen wir für Inferenz? | MI |  |  | active | D1.3.4 | Inference ARM: Out of the box inference with defined networks with or without ARM-NN | Document, repository | * 1x Obj. Detection, 1x segmentation * Inference with ARM-NN: YoloV4 (Bck YoloV3), DeepLabV3, optional TFLite DeepLabV3+SSD-MobileNetV2, InceptionResNet * Guides in Github on how to setup the devices * Raspberry Pi environment completed |  | 1
| Inferenz Edge TPU: Inferenzmodul für Google Coral Stick erstellen | [39 empty] | 0% | Es soll Pytorch und TF ausführen können, Bericht im richtigen Format zurückgeben, wenn Daten und Modell bekannt sind. Der Coral stick könnte am NUC hängen und über den NUC angesteuert werden | Pausiert |  |  | [] Edge TPU an NUC anhängen und zum Laufen zu bringen [] Inference scripts wie aus OpenVino vorbereiten
| Inferenz ARM Processor für TF und Pytorch ermöglichen | [38 empty] | 3 | 10% |  |  | MI
WP1.3.5 | Inferenz an Xilinx ermöglichen | [36 empty] | 2020-10-01 | 2021-05-30 |  | 15% | Inference on Xilinx ZCU102 | Welche Hardware noch wollen wir für Inferenz? | MWU |  |  | active | D1.3.5 | Inference Xilinx: Out of the box inference with defined networks with or without Vitis-AI | Document, repository | * 1x Obj. Detection, 1x segmentation * Inference with Vitis-AI: YoloV4 (Bck YoloV3) * Guides in Github on how to setup the devices * Raspberry Pi environment completed |  | 1
| Inferenz Xilinx Processor für TF und Pytorch ermöglichen | [38 empty] | 4 | 30% | Inferenz am Xilinx machen. Vitis Software aufsetzen |  | Marco |  | [] Vitis installieren | bar: 2020 11 14 to 2021 1 16
| Inferenz Xilinx durch NVIDIA NVDLA Inferenz ermögichen auf einer Xilinx-Plattform | [38 empty] | 4 | 0% |  |  | MW
WP1.3.6 | Powermessungen für NCS2 und NVIDIA ermöglichen | [36 empty] | 2020-07-01 | 2020-03-31 |  | 30.68% | Allow power measurements for common HW |  | MI |  |  | active | D1.3.6 | Single networks power measurements | Script, guide | * Scripts for power measurements |  | 2
| Powermessungen von NCS2 möglich | [38 empty] | 3 | 80% | Setup für Hardwaremessungen am NCS2 vorhanden | Großer Shunt 1 Ohm, Last 10 Ohm. Messung beeinflusst. USB 201 Messgerät. Problem ist USB-Anschlüsse | MI |  | [] Messaufbau verfeinern [] Löten auf ein Perfboard [] Platz im Labor für Messungen machen | bar: 2020 10 13 to 2020 12 15
| Softwareinterface für Powermessungen USB Geräte fertig | [38 empty] | 3 | 95% | Softwaresteuerung für die Messung. Setzen von Sampling rate, Flags, Speichern und anzeigen | Script für USB-Messungen fertig | MI |  | [] Scripts in Github [] Optional: Trigger hinzufügen fürs Staren von Messungen | bar: 2020 12 15
| Powermessungen von Jetson Nano möglich | [38 empty] | 3 | 50% |  | Stephan Hollys Messmethode | MI |  | [] Messmethode | bar: 2020 10 13
| Softwareinterface für Powermessungen am NVIDIA-Geräte erstellen | [38 empty] | 3 | 0%
| Powermessungen ARM Raspberry PI ermöglichen | [38 empty] | 2 | 0% |  |  | MI | bar: 2021 1 16
| Softwareinterface für Powermessungen am Raspberry PI erstellen | [38 empty] | 2 | 0% |  |  | MI | bar: 2021 1 16
| Powermessungen Xilinx ermöglichen | [38 empty] | 3 | 0% |  |  | MW
| Softwareinterface für Powermessungen am Xilinx erstellen | [38 empty] | 3 | 0% |  |  | MW
WP1.3.7 | Systemintegration | [37 empty] | 2021-03-31 |  | 0% | Demonstration and documentation |  | AW |  |  | open | D1.3.7 | Inference of common neural networks available on all hardware | Document, validation networks | * Overview matrics of the possibility to do inference with a certain framework on a certain hardware in the laboratory * Guides how to setup the environments * Guides how to do inference with a pretrained model * Validation networks for each framework |  | 3
| Demonstration Inferenz eines SSDMobileNetV3 auf Xavier, NCS2 und ANETTE und Neural Power | [38 empty] | 2 | 0% | Ergebnis 6 Latenzen + Layerzeiten geschätzt und wirklich, 2 wirkuche, 4 geschätzte |  | AW | bar: 2021 1 16
| Dokumentation aller erzeugten Modulen und Open Source | [38 empty] | 2 | 0% | Modul aufsetzen, Requirement.txt, Doku schreiben, Code und Doku auf Github legen |  | AW | bar: 2021 1 16
WP2.1 | Quantization | [39 empty] | 15% |  | Wollen wir weitere Quantisierungen anschauen? | bar: 2019 10 1 to 2020 12 15
WP2.1.1 | HW unabhängige Quantization | [36 empty] | 2020-03-01 |  |  | 40% | HW independent quantization on Xilinx |  | MW | DD |  | active | D2.1.1 | Quantization of fully connected und conv layer prunable, TinyYoloV3, ResNet | Document | * Repository with software module * Comprison with Vitis AI, für Yolo, ResNet and supported layer * Thesis |  | 3
| Algorithmus von Dominik (Quantization) fertigstellen | [38 empty] | 4 | 60% |  | Was wird quantisiert? Weight oder alles? Mixed Quantization machen? - VITIS installiert Yolonetz zu Caffe umwandeln | DD |  | [] Vergleich mit anderen Tools machen eigenen mit anderen Quantization Tools: VITIS [] Tiny Yolo quantizieren [] Arbeit schreiben | bar: 2020 4 7 to 2021 2 17
| Dominiks Quantizationalgorithmus als Softwarepaket erstellen | [38 empty] | 2 | 0% | Interface an Algorithmus anschließen (Algoritmus als Blackbox betrachten); Algorithmus lokal demonstrieren (alles auf einem PC mit Inferenz direkt am Gerät); |  | AW | bar: 2020 11 14 to 2021 3 18
WP2.1.2 | NVIDIA Native Quantization | [36 empty] | 2020-11-01 |  |  | 0% | Test Tensor-RT native quantization |  | AW | KK |  | active | D2.1.2 | Effects of quantization through tensor-rt known | Document | * Part of the bachelor thesis: Measurements of latency and acc. Of MobileNet variants w/o trt quantization |  | 2
| NVIDIA Tensor-RT Quantizationmethoden untersuchen | [38 empty] | 2 | 0% |  |  | KK
WP2.1.3 | Intel Native Quantization | [36 empty] | 2020-10-01 |  |  | 0% | Test OpenVino native quantization |  | AW | JW |  | active | D2.1.3 | Effect of quantization through OpenVino known | Document | * Part of the bachelor thesis: Measurements of MobileNet TF1 variants latency and acc. w/o openvino quantization |  | 2
| OpenVino Quantizationmethoden untersuchen | [38 empty] | 2 | 0% |  |  | JW
WP2.1.4 | One-shot Quantizeable Slimmable Adaptive Networks on Xilinx | [36 empty] | 2020-10-01 | 2021-07-30 |  | 10% | Tradeoff between slimmable networks and quantization regarding performance loss and latency gain |  | MW | BS |  | active | D2.1.4 | Tradeoff between slimmable networks and quantization regarding performance loss and latency gain on State-of-the-Art Architectures | Repositor, Master Thesis | * Results for training Slimmable Networks and Adabits Networks at the Same Time * Repository to apply Methodology on other Networks |  | 1
| Arbeit Slimmable Networks Adabits zusammenfügen | [38 empty] | 3 | 10% | Optimum zwischen Pruning und Quantization. Ziel: Quantization drinnen ist und Batchnormalization integriert im Netzwerk | bar: 2020 11 14 to 2021 1 16
| Evaluieren mit unterschiedlichen Einstellungen, Pareto Opt finden | [38 empty] | 3 | 0% | Paretooptimum finden zwischen Pruning und Quantization. | bar: 2021 2 17 to 2021 4 19
| Welche Effekte mehr auf der HW | [38 empty] | 2 | 0% | bar: 2021 5 20 to 2021 6 21
WP2.2 | Pruning | [39 empty] | 30.71% |  | Welche andere Pruningmethoden wollen wir anschauen? | bar: 2019 10 1 to 2020 12 15
WP2.2.1 | Distiller HW unabhängiges Pruning | [36 empty] | 2020-03-01 |  |  | 66.67% | HW independent pruning through distiller |  | ML | AG |  | active | D2.2.1 | Distiller derived pruning tool for simple networks ResNets for classification tasks as well as MobileNet | Thesis, Publication, Repository | * Enhancement of Distiller pruning tool * Performane comparison to a depth multipler at MobileNet * ResNet classification netzwork * Software Tool for Pytorch inputs |  | 3
| Algorithmus von Andreas (Pruning) fertigstellen und einschließen | [38 empty] | 5 | 80% |  | Geht mit ResNet. Segmentation fault | AG | bar: 2020 6 9 to 2021 1 16
| Andreas Pruningalgorithmus als Softwarepaket erstellen | [38 empty] | 1 | 0% | Interface an Algorithmus anschließen (Algoritmus als Blackbox betrachten); Algorithmus lokal demonstrieren (alles auf einem PC mit Inferenz direkt am Gerät); | Tensor-rt Umwandlung geht nicht | AW | bar: 2020 11 14 to 2021 2 17
WP2.2.2 | Netzoptimierung durch slimmable Networks | [36 empty] | 2020-10-01 |  |  | 3.75% | Application of slimmable networks MobileNet on NVIDIA |  | MW | KK |  | active | D2.2.2 | Knowledge if slimmable networks better than MobileNet Depth multipler | Document, repository | * Bach. Thesis: Implementation of slimmable networks on MobileNet on NVIDIA. Compare performance with depth multiplier * Comparison of latency and acc. On device * repository with setup and execution scripts |  | 2
| Reproduce results on MobileNet2 | [38 empty] | 1 | 30% | Download code from repository https://github.com/JiahuiYu/slimmable_networks, let examples run locally on ICT Server, reproduce the results on the provided MobileNetV2 on ImageNet Subset, read and understand papers, research accuracy & latency measure options, Quantization methods |  | KK | bar: 2020 11 14
| Setup tensor-rt on NVIDIA Jetson Nano | [38 empty] | 1 | 0% |  |  | KK | bar: 2020 12 15
| Experiment on MobileNetV2 | [38 empty] | 1 | 0% | On Jetson Nano |  | KK | bar: 2020 12 15
| Experiment on Slimmed MobileNetV2 | [38 empty] | 1 | 0% | Slimmable networks, universally slimmable networks, autoslim on Jetson Nano |  | KK | bar: 2020 12 15
| Experiment on quantized MobileNetV2 | [38 empty] | 1 | 0% |  |  | KK | bar: 2020 12 15
| Experiment on quantized slimmed MobileNetV2 | [38 empty] | 1 | 0% |  |  | KK | bar: 2021 1 16
| Explore how to implement latency optimization | [38 empty] | 1 | 0% | how to implement hardware aware latency optimizations for slimmable MobileNetV2 |  | KK | bar: 2021 1 16
| Evaluate performance and latency of different nw | [38 empty] | 1 | 0% | MobileNetV2, 3 Slimmable MobileNetV2 versions, quantized and or slimmed versions |  | KK | bar: 2021 1 16
WP2.3 | Factorization | [39 empty] | 0% |  | Hier haben wir nichts. Was machen wir? | bar: 2019 10 1 to 2020 12 15
[40 empty] | 5 | 0%
WP2.4 | Compact Design | [39 empty] | 55.93% | bar: 2020 3 6 to 2021 2 17
WP2.4.1 | Shuntconnections für MobileNet | [36 empty] | 2020-08-01 | 2020-02-28 |  | 78.33% | Replace blocks of MobileNet with shunt connections to reduce FLOPS |  | BH | BH |  | active | D2.4.1 | Proof of concept of Knowledge distillation and shunt connections for segmentation networks. Provide an easy-to-use open-source software tool for inserting shunt connections into existing Keras networks | Publication, Master Thesis, Repository | * Results for training shunt connections using knowledge distillation both for classification and segmentation networks * Inference results on NVIDIA, Xilinx and Raspberry Pi platforms * Keras based Python3 package for shunt connections * Some common network architectures available through the software (MobileNetV2/3, DeeplabV3) * Limited custom network support * Open*source solution provided through GitHub |  | 1
| Algorithmus von Bernhard (Shuntconnections) fertigstellen | [38 empty] | 5 | 80% |  | *Imagenet dauert zu lange (10h). Eine Epoche 30min *Finetuning war erfolgreich, Knowledge Distillation abgeschlossen *Imagenet 3% geringer als vortrainiertes Netz (68% statt 71%). Preprocessing unklar. Mit der richtigen Config sollte es passen *Testbereit Anfang Dezember | BH |  | [x] GPU-Erweiterung auf 2 GPUs: Funktioniert [x] Finetuning auf Imagenet [] Übertragen auf Deeplab [] Inference on NVIDIA HW [] Inference on Intel-HW [] Inference on Raspberry PI (Only CPU) [] Thesis written |  | D2.4.1.1 | bar: 2020 7 10 to 2021 1 16
| Bernhards Algorithmus als Softwarepaket erstellen | [38 empty] | 1 | 70% | Interface an Algorithmus anschließen (Algoritmus als Blackbox betrachten); Algorithmus lokal demonstrieren (alles auf einem PC mit Inferenz direkt am Gerät); |  | BH |  |  |  | D2.4.1.2 | bar: 2021 2 17 to 2021 3 18
WP2.4.2 | SqueezeNas Modelle trainieren | [36 empty] | 2020-04-01 |  |  | 85% | Reimplement SqueezeNAS for semantic segmentation. Compare to Deeplab |  | AM |  |  | active | D2.4.2 | Retraining the SqueezeNAS networks on the RailSem dataset and comparing the inference results on Xavier with the results of CityScape | Document, Repository | *Preprocessing of the data *Latency values on NVIDIA Xavier *IoU scores for the RailSem results *Comparison of RailSem and CityScape on squeezenas *Performance and latency comparison with DeepLab |  | 2
| Raildatenset für Training am Server aufbereiten | [38 empty] | 2 | 100% |  |  | AM
| Metriken und Scripts für IoU-Messungen beim Inferenz erstellen | [38 empty] | 2 | 80% | IoU berechnen. Visualisierung davon |  | AM |  | [] Script für IoU und Visualisierung erstellen | bar: 2020 9 12 to 2020 12 15
| SqueezeNas Modelle M, L, XL mit Raildatenset trainieren | [38 empty] | 4 | 80% | 3 fertige Netzstrukturen für Xavier für Segmentationsnetze. Alle Modelle soll mit dem Raildatenset trainiert werden | *Trainieren geht *Gute IoU fehlt (15%, soll 50%-70%). Man soll mit MobileNet DeepLab trainieren *DeepLab wird getestet, laufend als Vergleich * | AM |  | [] Trainieren auf dem Server [] MobileNet + DeepLab als Referenz trainieren [] Herausfinden warum IoU schlecht ist | bar: 2020 9 12 to 2020 12 15
WP2.4.3 | Common Backbone for semantic and instance Segmentation | [36 empty] | 2020-09-01 |  |  | 30% | Use common MobileNet Backbone for both detection and segmentation | Welche Aufgaben stehen bevor? | AW | HB |  | active | D2.4.3 | Implementation of common MobileNet backbone | Thesis, repository | * Comparison acc and latency NVIDIA device of common backbone vs. separate networks * Common backbone implementation |  | 3
| Selection of state-of-the-art CNNs | [38 empty] | 2 | 100% | Networks: MobileNetV1[3], MobileNetV2[12], MobileNetV3[2] and EfficientNet[14]. | *Standardnetze mit oder ohne Optimierungen wie Shunt? | HB |  | [] Ein Netz auswählen | bar: 2020 9 12 to 2020 10 13
| Establishing of Baseline | [38 empty] | 2 | 50% | two networks for both object detection (with bounding boxes) and semantic segmentation will be built and trained separately. |  | HB | bar: 2020 9 12 to 2020 10 13
| Train/test the CNN for Object Detection | [38 empty] | 2 | 30% | For this fine-tuning or training the RailSem19[15] data set will be used. |  | HB | bar: 2020 11 14 to 2020 12 15
| Freezing the encoder, train/test/ fine-tune the segmentation CNN | [38 empty] | 2 | 0% | SDD trained. Segmentation CNN head will be trained using the feature maps from the encoder. Use RailSem19. Approach of having a shared encoder for both networks. |  | HB | bar: 2021 1 16
| Simultaneous train/test both networks | [38 empty] | 2 | 0% | Unified loss function and evaluation metric will be defined. | *Könnte man hier den Panoptic Segmentation Metric verwenden = F1(Det. RQ) * mean(IoU)(Seg. Q)? | HB | bar: 2021 2 17
| Comparison and evaluation | [38 empty] | 2 | 0% | Various settings: Different network models, hyper-parameters, and number of classes. Impact on runtime and accuracy will be evaluated. Latenz und Genauigkeit im Inference lösen |  | HB |  | [] Paper aus der Arbeit machen | bar: 2021 3 18 to 2021 4 19
WP2.4.4 | Comparison of YoloV3 vs. YoloV4 on a Xilinx | [36 empty] | 2021-03-01 | 2021-08-31 |  | 0% | Comparison of YoloV3 vs. YoloV4 on a Xilinx |  | ML | FS |  | paused | [5 empty] | 3
[40 empty] | 1 | 0%
WP2.5 | Optimization Strategy | [39 empty] | 42.36% |  | Target Plattform wäre Xilinx. Das haben wir noch nicht. Was machen wir? | bar: 2020 10 13 to 2021 9 24
WP2.5.1 | Trainingsserver EDA01 einrichten | [36 empty] | 2020-05-01 | 2021-01-31 |  | 96% | Get the training server ready for Pytorch and TF2 |  | AM |  |  | active | D2.5.1 | Server ready for training | Document | * Guides on how to setup EDA01 for different environments and training * Environments ready: Tensorflow 2, Pytorch |  | 2
| Dockercontainer(s) mit Tensorflow 2.3 und Pytorch für EDA01 einrichten | [38 empty] | 2 | 100% | Container einrichten, Pfade für Modelle, Daten und Parameter festlegen | Statt Container venv verwenden | AM | bar: 2020 9 12
| Startscripts für Containers/Trainingsumgebungen erstellen | [38 empty] | 1 | 100% | Standardisierte Scripts fürs Steuern der Containers. Hinzufügen von Jobs zum Task Scheduler | Frage ob noch offen nachdem wir ohne Containers trainieren können? *Nur 1 GPU verwendet. Besser wäre beide GPUs. *Andreas verwendet 2 GPUs, default in Pytorch? | BH |  | [] In TF beide GPUs verwenden | bar: 2020 10 13
| Demonstration der Funktionsweise von Environments/Containers | [38 empty] | 1 | 100% | Pytorch und TF Netzwerk aussuchen, z.B. MobileNetV2, Daten zum trainieren besorgen, z.B. Imagenet, Training mit Task spooler für beide Netze sequentiell ausführen, trainierte Modelle herunterladen |  | BH | bar: 2020 11 14
| Dokumentation des Aufsetzens und Bedienung des Trainings machen | [38 empty] | 1 | 80% | Die Arbeit dokumentieren, so dass andere es reproduzieren können und anwenden können | Doku von Marco ergänzen | BH | bar: 2020 11 14
WP2.5.2 | Externes Training einrichten | [36 empty] | 2020-10-01 | 2021-04-30 |  | 40% | Access to Amazon AWS and Vienna Scientific Cluster for training |  | AM |  |  | active | D2.5.2 | External services ready for training with our networks | Document | * Guide how to setup TF2, TF1 and Pytorch on Vienna Scientific Cluster * Guide how to train on Microsoft Azure |  | 2
| Cloud Services vergleichen | [38 empty] | 3 | 90% | Vergleich von Amazon AWS, Microsoft unf Google bezüglich Funktion, Bedienbarkeit und Preis | Analyse abgeschlossen. Bachelorarbeit fast fertig | AW | JR | [] Bachelorpräsentation | bar: 2020 11 14 to 2020 12 15
| Microsoft Azure für Training einrichten | [38 empty] | 2 | 0% | Umgebung oder Container einrichten, um auf Azure auch trainieren zu können. Ergebnis: Script, womit man wie beim EDA trainieren kann | Nicht angefangen, optional | AW | bar: 2021 3 18 to 2021 4 19
| Vienna Scientific Cluster für Training einrichten | [38 empty] | 2 | 80% | Zugriff auf dem Scientific Cluster. Aufgabe fertig, wenn Bernhard darauf erfolgreich trainiert hat | Training mit TF2 läuft. TF1 soll gehen, wurde aber noch nicht probiert | BH |  | [] Doku in Github [] Test mit TF1 | bar: 2020 9 12 to 2020 12 15
WP2.5.3 | Messdatenbank für Messungen im Labor einrichten | [39 empty] | 0% | Collect all measurements from devices |  | AW |  |  | open | [5 empty] | 3
| TU Server für Datenbank aufsetzen | [38 empty] | 1 | 0% | Server von Daniel bekommen mit geeigneter Software |  | AW
| Datenbankschema und Technologie auswählen | [38 empty] | 1 | 0% | z.B. PostgreSQL; Schema aus den Inferenzberichten erstellen; |  | AW
| Datenbankschnittstelle erstellen | [38 empty] | 1 | 0% | Scripts erstellen; Services für Datenbankzugriff öffnen; |  | AW
| Datenbankbetrieb demonstrieren | [38 empty] | 1 | 0% | Demonstrieren mit einem Netz, das auf Xavier Inferenz ausführt und die Metadaten + Ausführungslatenz speichert |  | AW
WP2.5.4 | EML-Prozess automatisieren und vereinfachen | [39 empty] | 0% | Automate manual inference steps |  | AW |  |  | open | [5 empty] | 3
| Softwaremodul für Schnittstelle Geräte zu Pythonsoftware schreiben | [38 empty] | 3 | 0% | Pythonmethoden für einheitliches Ausführen von Latenzmessungen an Hardware, wo IP bekannt ist und Typ. Einbindung von Protokollen und Parsern |  | Marco | bar: 2020 11 14 to 2020 12 15
| Gemeinsame Schnittstelle der Optimierungsalgorithmen definieren | [38 empty] | 3 | 0% | Herausfinden wie Inputs und Outputs aussehen; Bedarf nach Retraining und Inferenz auf einem Gerät ermitteln; Schnittstelle definieren; Implementierungstechnologie wählen (Docker?) |  | AW | bar: 2020 11 14
WP2.5.5 | Applikation: Traffic Light System | [36 empty] | 2020-03-01 |  |  | 13.33% | Traffic Light System: Find best combination of HW device and network MobileNet, EfficientDet and Yolo for a pedestrian detection application |  | AW | JW |  | active | D2.5.5 | Optimal network, hardware and hardware configuration | Document | * Evaluation of EfficientDet, SSD-MobileNet and Yolo on NVIDIA, Edge TPU * Pedestrian training dataset from official sources |  | 2
| Netzwerke, Optimierungsalgorithmen und Testhardware defineren | [38 empty] | 3 | 20% | Festlegen welche Netzwerke angeschaut werden, MobileNetV1,2,3, Auflösungen und Depth zu testen. HW festlegen: NUC, NCS2, NVIDIA alle Plattformen. Alle Netzwerke sollen in Netron darstellbar sein | * Netze noch nicht in Netron darstellbar | AW |  | [] TF2 frozen zu mmdnn konvertieren | bar: 2020 11 14 to 2020 12 15
| Pedestrian Datenset vorbereiten | [38 empty] | 2 | 50% | Datenset von allen Formaten in Coco oder Pascal Voc umwandeln und dann in TF Records |  | AW | JW | bar: 2020 11 14 to 2021 1 16
| Train MobileNet, EfficientDet, Yolo with data | [38 empty] | 1 | 0% | MobileNet V2 TF1 und TF2, EfficientDet TF2, Yolo |  | AW | bar: 2021 1 16 to 2021 3 18
| Setup test hardware | [38 empty] | 3 | 0% | Aufsetzen von NVIDIA, Edge-TPU und NUC und NCS2 |  | AW | bar: 2021 1 16 to 2021 4 19
| Inference on HW with pretrained networks | [38 empty] | 2 | 0% | Inferenz an NVIDIA, Edge-TPU, NUC und NCS2 |  | AW | bar: 2021 2 17 to 2021 4 19
| Evaluation of Networks and Performance | [38 empty] | 1 | 0% | Visualisierung, beste Kombination ermitteln | bar: 2021 4 19 to 2021 5 20
WP2.5.6 | Applikation: Ragweederkennung über eine Drohne | [36 empty] | 2020-08-01 |  |  | 42% | Recognize Ragweed from a drone. Optimize Network on NVIDIA devices |  | AW | LS |  | active | D2.5.6 | Optimal network, hardware and hardware configuration | Document, Pretrained network | * Evaluation of performance and latency of segmentation network on NVIDIA * Trained network in repository * Ragweed dataset |  | 3
| Datensammlung | [38 empty] | 2 | 100% |  |  | LS | bar: 2020 9 12
| Daten labeln | [38 empty] | 2 | 80% | videos dabei overlapping croppen. | Alle Daten nicht gelabelt, aber es ist genug da. Jedes Format kann exportieren. Semantic segmentation offen | LS | bar: 2020 9 12
| Objektdetector-Modelle trainieren | [38 empty] | 2 | 70% |  | [] Ground Truth in Tensorboard darstellen. Segementation modell | LS |  | [] Das beste Baselinemodell finden und trainieren | bar: 2020 10 13 to 2020 12 15
| Deployment auf Embedded Devices | [38 empty] | 2 | 2% |  |  | LS | bar: 2020 12 15 to 2021 1 16
| Messungen der Leistung und des Energieverbrauchs der verschiedenen Modelle auf den verschiedenen Devices | [38 empty] | 2 | 0% |  |  | LS | bar: 2020 12 15 to 2021 1 16
| Zusammenfassung der Ergebnisse und verfassen der Diplomarbeit | [38 empty] | 2 | 0% |  |  | LS | bar: 2021 1 16 to 2021 3 18
WP2.5.7 | Applikation: Minicar Demonstrator | [36 empty] | 2020-01-01 |  |  | 93.33% | Minicar demonstrator for execution of detection networks on Raspberry Pi |  | MI | MI |  | active | D2.5.7 | Running demonstrator for neural networks | Repository, Model car, Bachelor Thesis | * Modified model car, which can be controlled by WiFI, video feed with camera image, bounding boxes with classes painted into the image by an object detection network * Software project with scripts necessary to run the demonstrator * Written thesis about the demonstrator * Video with visible comparsion of networks and modi |  | 3
| Stabil laufende Objekterkennung im Stream | [38 empty] | 4 | 100% |  | - Steuerung fertig. Neue Version verzögert die Entwicklung - Das Fahren geht gut | MI | bar: 2020 9 12 to 2020 11 14
| Software Switch für Netzwerke/Modi | [38 empty] | 1 | 40% |  | - Flask einsetzen | MI |  | [] Flask mit Subprozessen aufsetzen | bar: 2020 10 13 to 2020 12 15
| Inferenz am RPi laufen lassen (tflite conversion + inference) + Video drehen | [38 empty] | 4 | 100% | Video drehen mit Inferenz | Object Detection braucht andere Frontend, Yolo anderes Frontend MobileNet. Inferenz mit Tflite geht (nur classification). Tflite Yolov3 Tiny geht. Langsam | MI | bar: 2020 11 14 to 2021 1 16
WP2.5.8 | Applikation: TFLite Netz auf einem Handy | [36 empty] | 2020-10-01 |  |  | 28.33% | Mobile phone demonstrator for detection |  | AW | TK |  | active | D2.5.8 | Android handy with custom object detection in TF | Document, SW package | * Guide how to setup app for TF Obj. Detection API TF2 * App installed on mobile phone * Coco Pretrained test network |  | 3
| Netz zu TFLite umwandeln | [38 empty] | 1 | 20% |  | - SSD-MobileNetV2 auf Coco trainiert wird | bar: 2020 11 14
| Androidapp entwickeln | [38 empty] | 3 | 50% | bar: 2020 12 15
| Bericht erstellen - Ausführungszeiten | [38 empty] | 1 | 0% | bar: 2021 1 16
| Demonstrieren wie man ein vortrainiertes Netz auf das Telefon bringen kann | [38 empty] | 1 | 0% | bar: 2021 2 17
Formatting
Task *
Workpackage w
Subtask s
Delayed d
Prolonged p
Offiziellen Milestones
M1.1: Estimation techniqe
M1.2: Optimization technique
M1.3: Design flow
MS2.1 Compression Technique Performance Comparison
MS2.2 Design Methodology
MS2.3 Design & Optimization Methodology
MS3.1 Preliminary Dataset, Baseline
MS3.2 On-line Learning System
Submilesontes
Deliverables

## Autogenerate_Work_Progress
WP ID | Title | Start Date | Expected End | Description | Responsible | Student | Result | Deliver. | Progress | State | Prio
WP1.1 | Create estimations for lat, throughput, power, energy, acc, resources |  |  | Create estimations for lat, throughput, power, energy, acc, resources
WP1.1.1 | State of the Art Latency und Power Estimation Modelle aufsetzen | 2020-09-01 | 2020-10-30 | Setup Neural Power latency and power estimation model | Marco Wuschnig |  | Publication | D1.1.1 | 100% | completed
WP1.1.2 | Estimator Blackthorn for Latency (NVIDIA) | 2019-10-01 | 2021-02-28 | Model based latency estimator method | Martin Lechner | Martin Lechner | Repository, Publication | D1.1.2 | 81.11% | active | 1
WP1.1.3 | Estimator method ANETTE for Latency (Intel, ARM, Xilinx) | 2019-10-01 | 2021-02-28 | Statistic and model based latency estimator method | Matthias Wess | Matthias Wess | Repository, Publication | D1.1.3 | 54% | active | 1
WP1.1.4 | Estimation of Power through a White box model | 2020-08-01 | 2020-10-30 | Power estimation through circuit simulator | Christian Krieg |  |  |  | 20% | paused | 3
WP1.1.5 | Estimation of Power through ANETTE |  |  | Power estimation through the estimator ANNETTE | Matthias Wess |  |  |  | 0% | open | 2
WP1.1.6 | Estimation of On-Chip Resources |  |  | Estimate resources like memory usage | Martin Lechner |  |  |  | 0% | open | 3
WP1.2 | Optimize HW Dependent Settings |  |  | Optimize HW Dependent Settings
WP1.2.1 | NVIDIA Profiling | 2020-03-01 | 2021-03-31 | HW settings profiling of NVIDIA Xavier, Jetson Nano (Bachelor thesis) and TX2 | Stephan Holly | Stephan Holly | Bachelor thesis, Publication, Documentation | D1.2.1 | 35.56% | active | 1
WP1.2.2 | ARM Profiling | 2020-11-01 | 2021-02-28 | HW settings profiling of Raspberry Pi | Matvey Ivanov |  | Repository, Document | D1.2.2 | 46% | active | 1
WP1.2.3 | Xilinx Profiling | 2020-11-01 |  | HW settings profiling of Xilinx ZCU102 | Marco Wuschnig |  | Document | D1.2.3 | 6.667% | active | 1
WP1.2.4 | Intel Profiling | 2019-10-01 | 2020-03-31 | HW settings profiling of Intel NCS2 and CPU through OpenVino | Matvey Ivanov |  | Document, thesis | D1.2.4 | 60% | active | 3
WP1.3 | Map Models of hardware |  |  | Map Models of hardware
WP1.3.1 | Gemeinsame Infrastruktur Hardwareschnittstelle |  |  | Common software interfaces for devices | Marco Wuschnig |  |  |  | 15% | open | 3
WP1.3.2 | Inferenz an NVIDIA Hardware ermöglichen | 2020-03-01 | 2020-03-31 | Inference on Nano, TX2 and Xavier | Amid Mozelli |  | Document, repository | D1.3.2 | 12.5% | active | 1
WP1.3.3 | Inferenz an Intelgeräte ermöglichen | 2019-10-01 | 2021-01-31 | Inference on NUC and NCS2 | Matvey Ivanov |  | Document, repository | D1.3.3 | 91.25% | active | 2
WP1.3.4 | Inferenz an ARM ermöglichen | 2020-10-01 | 2021-02-28 | Inference on Raspberry Pi | Matvey Ivanov |  | Document, repository | D1.3.4 | 10% | active | 1
WP1.3.5 | Inferenz an Xilinx ermöglichen | 2020-10-01 | 2021-05-30 | Inference on Xilinx ZCU102 | Marco Wuschnig |  | Document, repository | D1.3.5 | 15% | active | 1
WP1.3.6 | Powermessungen für NCS2 und NVIDIA ermöglichen | 2020-07-01 | 2020-03-31 | Allow power measurements for common HW | Matvey Ivanov |  | Script, guide | D1.3.6 | 30.68% | active | 2
WP1.3.7 |  |  | 2021-03-31 | Demonstration and documentation | Alexander Wendt |  | Document, validation networks | D1.3.7 | 0% | open | 3
WP2.1 | Quantization |  |  | Quantization
WP2.1.1 | HW unabhängige Quantization | 2020-03-01 |  | HW independent quantization on Xilinx | Matthias Wess | Dominik Dallinger | Document | D2.1.1 | 40% | active | 3
WP2.1.2 | NVIDIA Native Quantization | 2020-11-01 |  | Test Tensor-RT native quantization | Alexander Wendt | Karoline Knoth | Document | D2.1.2 | 0% | active | 2
WP2.1.3 | Intel Native Quantization | 2020-10-01 |  | Test OpenVino native quantization | Alexander Wendt | Julian Westra | Document | D2.1.3 | 0% | active | 2
WP2.1.4 | One-shot Quantizeable Slimmable Adaptive Networks on Xilinx | 2020-10-01 | 2021-07-30 | Tradeoff between slimmable networks and quantization regarding performance loss and latency gain | Matthias Wess | Birgit Schreiber | Repositor, Master Thesis | D2.1.4 | 10% | active | 1
WP2.2 | Pruning |  |  | Pruning
WP2.2.1 | Distiller HW unabhängiges Pruning | 2020-03-01 |  | HW independent pruning through distiller | Martin Lechner | Andreas Glinserer | Thesis, Publication, Repository | D2.2.1 | 66.67% | active | 3
WP2.2.2 | Netzoptimierung durch slimmable Networks | 2020-10-01 |  | Application of slimmable networks MobileNet on NVIDIA | Matthias Wess | Karoline Knoth | Document, repository | D2.2.2 | 3.75% | active | 2
WP2.3 | Factorization |  |  | Factorization
WP2.4 | Compact Design |  |  | Compact Design
WP2.4.1 | Shuntconnections für MobileNet | 2020-08-01 | 2020-02-28 | Replace blocks of MobileNet with shunt connections to reduce FLOPS | Bernhard Haas | Bernhard Haas | Publication, Master Thesis, Repository | D2.4.1 | 78.33% | active | 1
WP2.4.2 | SqueezeNas Modelle trainieren | 2020-04-01 |  | Reimplement SqueezeNAS for semantic segmentation. Compare to Deeplab | Amid Mozelli |  | Document, Repository | D2.4.2 | 85% | active | 2
WP2.4.3 | Common Backbone for semantic and instance Segmentation | 2020-09-01 |  | Use common MobileNet Backbone for both detection and segmentation | Alexander Wendt | Helmuth Breitenfellner | Thesis, repository | D2.4.3 | 30% | active | 3
WP2.4.4 | Comparison of YoloV3 vs. YoloV4 on a Xilinx | 2021-03-01 | 2021-08-31 | Comparison of YoloV3 vs. YoloV4 on a Xilinx | Martin Lechner | Fabian Scherer |  |  | 0% | paused | 3
WP2.5 | Optimization Strategy |  |  | Optimization Strategy
WP2.5.1 | Trainingsserver EDA01 einrichten | 2020-05-01 | 2021-01-31 | Get the training server ready for Pytorch and TF2 | Amid Mozelli |  | Document | D2.5.1 | 96% | active | 2
WP2.5.2 | Externes Training einrichten | 2020-10-01 | 2021-04-30 | Access to Amazon AWS and Vienna Scientific Cluster for training | Amid Mozelli |  | Document | D2.5.2 | 40% | active | 2
WP2.5.3 | Messdatenbank für Messungen im Labor einrichten |  |  | Collect all measurements from devices | Alexander Wendt |  |  |  | 0% | open | 3
WP2.5.4 | EML-Prozess automatisieren und vereinfachen |  |  | Automate manual inference steps | Alexander Wendt |  |  |  | 0% | open | 3
WP2.5.5 | Applikation: Traffic Light System | 2020-03-01 |  | Traffic Light System: Find best combination of HW device and network MobileNet, EfficientDet and Yolo for a pedestrian detection application | Alexander Wendt | Julian Westra | Document | D2.5.5 | 13.33% | active | 2
WP2.5.6 | Applikation: Ragweederkennung über eine Drohne | 2020-08-01 |  | Recognize Ragweed from a drone. Optimize Network on NVIDIA devices | Alexander Wendt | Lukas Steindl | Document, Pretrained network | D2.5.6 | 42% | active | 3
WP2.5.7 | Applikation: Minicar Demonstrator | 2020-01-01 |  | Minicar demonstrator for execution of detection networks on Raspberry Pi | Matvey Ivanov | Matvey Ivanov | Repository, Model car, Bachelor Thesis | D2.5.7 | 93.33% | active | 3
WP2.5.8 | Applikation: TFLite Netz auf einem Handy | 2020-10-01 |  | Mobile phone demonstrator for detection | Alexander Wendt | Thomas Kotrba | Document, SW package | D2.5.8 | 28.33% | active | 3
Formulas:
Start Date = IF(VLOOKUP([WP ID],EML_Tool_WP!A:BB,39,FALSE)="","",VLOOKUP([WP ID],EML_Tool_WP!A:BB,39,FALSE))
Expected End = IF(VLOOKUP([WP ID],EML_Tool_WP!A:BB,40,FALSE)="","",VLOOKUP([WP ID],EML_Tool_WP!A:BB,40,FALSE))

## Autogenerate_Deliverables
WP | ID | Title | Responsible | E. End Date | Goal | Type | Content
WP1.1 |  | Create estimations for lat, throughput, power, energy, acc, resources
WP1.1.1 | D1.1.1 | State of the Art Latency und Power Estimation Modelle aufsetzen | Marco Wuschnig | 2020-10-30 | Baseline for own estimators | Publication | * included in the publication of ANNETTE
WP1.1.2 | D1.1.2 | Estimator Blackthorn for Latency (NVIDIA) | Martin Lechner | 2021-02-28 | Estimation model for Embedded (Nvidia) Platforms | Repository, Publication | * Publication * Benchmarking Results and Estimation Models for NVIDIA * Repository on Github (Open source)
WP1.1.3 | D1.1.3 | Estimator method ANETTE for Latency (Intel, ARM, Xilinx) | Matthias Wess | 2021-02-28 | Estimator method ANETTE for Latency (Intel, ARM, Xilinx) | Repository, Publication | * Publication of ANNETTE * Benchmark Results of NCS2 Platform * Benchmark Results of Xilinx Platform * Benchmark Results of ARMNN Example Platform * Prediction Models for all three platforms * Open Source Repository for Latency Estimation
WP1.1.4 | 0 | Estimation of Power through a White box model | Christian Krieg | 2020-10-30
WP1.1.5 | 0 | Estimation of Power through ANETTE | Matthias Wess
WP1.1.6 | 0 | Estimation of On-Chip Resources | Martin Lechner
WP1.2 |  | Optimize HW Dependent Settings
WP1.2.1 | D1.2.1 | NVIDIA Profiling | Stephan Holly | 2021-03-31 | Latency, power and energy profiling of HW options of NVIDIA Jetson Nano, Xavier, TX2 | Bachelor thesis, Publication, Documentation | * Power measurements * Batchsizes 1-4 * Variation of possible HW options e.g. GPU frequency * Analysis of power peaks and settings definition to prevent overheating
WP1.2.2 | D1.2.2 | ARM Profiling | Matvey Ivanov | 2021-02-28 | Evaluation of an ARM CPU | Repository, Document | * Guide how to setup ArmNN and TFLite for 32 and 64 bit of a Raspberry Pi 4 (32/64 Bit) * Software projectwith benchmarks, test, conversion, inferenz*Scripts for ArmNN * Table with latency comparison of ArmNN and TFLite 32/64 Bit with inference with an ordinary accelerator
WP1.2.3 | D1.2.3 | Xilinx Profiling | Marco Wuschnig |  |  | Document | * Analysis how many needed kernels, share of FPGA used, consequences of consumes power, tradeoff between speedup and power * Repository * Inference possible
WP1.2.4 | D1.2.4 | Intel Profiling | Matvey Ivanov | 2020-03-31 |  | Document, thesis | * Evaluation of stick sync vs. async mode and other settings of NCS2 as part of thesis MW * Results included in ANNETTE D1.1.3
WP1.3 |  | Map Models of hardware
WP1.3.1 | 0 | Gemeinsame Infrastruktur Hardwareschnittstelle | Marco Wuschnig
WP1.3.2 | D1.3.2 | Inferenz an NVIDIA Hardware ermöglichen | Amid Mozelli | 2020-03-31 | Inference NVIDIA: Out of the box inference with defined networks with or without tensor-rt | Document, repository | * 1x Obj. Detection, 1x segmentation * Inference with tensor-rt: YoloV4 (Bck YoloV3), DeepLabV3, SSD-MobileNetV2, Object Detection API 2.0 * Guides in Github on how to setup the devices * Nano, TX2, Xavier environment completed
WP1.3.3 | D1.3.3 | Inferenz an Intelgeräte ermöglichen | Matvey Ivanov | 2021-01-31 | Inference Intel: Out of the box inference with defined networks with or without OpenVino | Document, repository | * 1x Obj. Detection, 1x segmentation * Inference with OpenVino: YoloV4 (Bck YoloV3), DeepLabV3, optional Object Detection API 2.0 SSD-MobileNetV2 * Guides in Github on how to setup the devices * NUC, NCS2 environment completed
WP1.3.4 | D1.3.4 | Inferenz an ARM ermöglichen | Matvey Ivanov | 2021-02-28 | Inference ARM: Out of the box inference with defined networks with or without ARM-NN | Document, repository | * 1x Obj. Detection, 1x segmentation * Inference with ARM-NN: YoloV4 (Bck YoloV3), DeepLabV3, optional TFLite DeepLabV3+SSD-MobileNetV2, InceptionResNet * Guides in Github on how to setup the devices * Raspberry Pi environment completed
WP1.3.5 | D1.3.5 | Inferenz an Xilinx ermöglichen | Marco Wuschnig | 2021-05-30 | Inference Xilinx: Out of the box inference with defined networks with or without Vitis-AI | Document, repository | * 1x Obj. Detection, 1x segmentation * Inference with Vitis-AI: YoloV4 (Bck YoloV3) * Guides in Github on how to setup the devices * Raspberry Pi environment completed
WP1.3.6 | D1.3.6 | Powermessungen für NCS2 und NVIDIA ermöglichen | Matvey Ivanov | 2020-03-31 | Single networks power measurements | Script, guide | * Scripts for power measurements
WP1.3.7 | D1.3.7 | Systemintegration | Alexander Wendt | 2021-03-31 | Inference of common neural networks available on all hardware | Document, validation networks | * Overview matrics of the possibility to do inference with a certain framework on a certain hardware in the laboratory * Guides how to setup the environments * Guides how to do inference with a pretrained model * Validation networks for each framework
WP2.1 |  | Quantization
WP2.1.1 | D2.1.1 | HW unabhängige Quantization | Matthias Wess |  | Quantization of fully connected und conv layer prunable, TinyYoloV3, ResNet | Document | * Repository with software module * Comprison with Vitis AI, für Yolo, ResNet and supported layer * Thesis
WP2.1.2 | D2.1.2 | NVIDIA Native Quantization | Alexander Wendt |  | Effects of quantization through tensor-rt known | Document | * Part of the bachelor thesis: Measurements of latency and acc. Of MobileNet variants w/o trt quantization
WP2.1.3 | D2.1.3 | Intel Native Quantization | Alexander Wendt |  | Effect of quantization through OpenVino known | Document | * Part of the bachelor thesis: Measurements of MobileNet TF1 variants latency and acc. w/o openvino quantization
WP2.1.4 | D2.1.4 | One-shot Quantizeable Slimmable Adaptive Networks on Xilinx | Matthias Wess | 2021-07-30 | Tradeoff between slimmable networks and quantization regarding performance loss and latency gain on State-of-the-Art Architectures | Repositor, Master Thesis | * Results for training Slimmable Networks and Adabits Networks at the Same Time * Repository to apply Methodology on other Networks
WP2.2 |  | Pruning
WP2.2.1 | D2.2.1 | Distiller HW unabhängiges Pruning | Martin Lechner |  | Distiller derived pruning tool for simple networks ResNets for classification tasks as well as MobileNet | Thesis, Publication, Repository | * Enhancement of Distiller pruning tool * Performane comparison to a depth multipler at MobileNet * ResNet classification netzwork * Software Tool for Pytorch inputs
WP2.2.2 | D2.2.2 | Netzoptimierung durch slimmable Networks | Matthias Wess |  | Knowledge if slimmable networks better than MobileNet Depth multipler | Document, repository | * Bach. Thesis: Implementation of slimmable networks on MobileNet on NVIDIA. Compare performance with depth multiplier * Comparison of latency and acc. On device * repository with setup and execution scripts
WP2.3 |  | Factorization
WP2.4 |  | Compact Design
WP2.4.1 | D2.4.1 | Shuntconnections für MobileNet | Bernhard Haas | 2020-02-28 | Proof of concept of Knowledge distillation and shunt connections for segmentation networks. Provide an easy-to-use open-source software tool for inserting shunt connections into existing Keras networks | Publication, Master Thesis, Repository | * Results for training shunt connections using knowledge distillation both for classification and segmentation networks * Inference results on NVIDIA, Xilinx and Raspberry Pi platforms * Keras based Python3 package for shunt connections * Some common network architectures available through the software (MobileNetV2/3, DeeplabV3) * Limited custom network support * Open*source solution provided through GitHub
WP2.4.2 | D2.4.2 | SqueezeNas Modelle trainieren | Amid Mozelli |  | Retraining the SqueezeNAS networks on the RailSem dataset and comparing the inference results on Xavier with the results of CityScape | Document, Repository | *Preprocessing of the data *Latency values on NVIDIA Xavier *IoU scores for the RailSem results *Comparison of RailSem and CityScape on squeezenas *Performance and latency comparison with DeepLab
WP2.4.3 | D2.4.3 | Common Backbone for semantic and instance Segmentation | Alexander Wendt |  | Implementation of common MobileNet backbone | Thesis, repository | * Comparison acc and latency NVIDIA device of common backbone vs. separate networks * Common backbone implementation
WP2.5 |  | Optimization Strategy
WP2.5.1 | D2.5.1 | Trainingsserver EDA01 einrichten | Amid Mozelli | 2021-01-31 | Server ready for training | Document | * Guides on how to setup EDA01 for different environments and training * Environments ready: Tensorflow 2, Pytorch
WP2.5.2 | D2.5.2 | Externes Training einrichten | Amid Mozelli | 2021-04-30 | External services ready for training with our networks | Document | * Guide how to setup TF2, TF1 and Pytorch on Vienna Scientific Cluster * Guide how to train on Microsoft Azure
WP2.5.3 | 0 | Messdatenbank für Messungen im Labor einrichten | Alexander Wendt
WP2.5.4 | 0 | EML-Prozess automatisieren und vereinfachen | Alexander Wendt
WP2.5.5 | D2.5.5 | Applikation: Traffic Light System | Alexander Wendt |  | Optimal network, hardware and hardware configuration | Document | * Evaluation of EfficientDet, SSD-MobileNet and Yolo on NVIDIA, Edge TPU * Pedestrian training dataset from official sources
WP2.5.6 | D2.5.6 | Applikation: Ragweederkennung über eine Drohne | Alexander Wendt |  | Optimal network, hardware and hardware configuration | Document, Pretrained network | * Evaluation of performance and latency of segmentation network on NVIDIA * Trained network in repository * Ragweed dataset
WP2.5.7 | D2.5.7 | Applikation: Minicar Demonstrator | Matvey Ivanov |  | Running demonstrator for neural networks | Repository, Model car, Bachelor Thesis | * Modified model car, which can be controlled by WiFI, video feed with camera image, bounding boxes with classes painted into the image by an object detection network * Software project with scripts necessary to run the demonstrator * Written thesis about the demonstrator * Video with visible comparsion of networks and modi
WP2.5.8 | D2.5.8 | Applikation: TFLite Netz auf einem Handy | Alexander Wendt |  | Android handy with custom object detection in TF | Document, SW package | * Guide how to setup app for TF Obj. Detection API TF2 * App installed on mobile phone * Coco Pretrained test network
Formulas:
E. End Date = IF(VLOOKUP([WP],EML_Tool_WP!A:BB,40,FALSE)="","",VLOOKUP([WP],EML_Tool_WP!A:BB,40,FALSE))

## Upcoming_Student_Thesis
Publish Date | Start Date | Type | Topic | Supervisor | Student | Comment | TISS Link | State
2020-02-28 |  | BA | Leistungsmessung einer GPU Plattform für Machine Learning Anwendungen | AW | S. Holly | NVIDIA Powerprofiling |  | Started
2020-03-30 |  | N/A | SqueezeNAS | AW | A. Mozelli | Netzwerkdesign |  | Started
2020-05-25 |  | MA | Compressing MobileNet With Shunt Connections for NVIDIA Hardware | AW | B. Haas | Netzwerkdesign |  | Started
2020-05-25 |  | MA | Optimizing DNNs for efficient dronebased ragweed detection | AW | L. Steindl | Ragweederkennung, Applikation |  | Started
2020-07-06 |  | BA | Cloudservices in der Lehre | AW | J. Roth | Amazon, Azure und Google testen |  | Started
2020-07-13 |  | MA | Simultanous Detection and Segmentation of Different Objects | AW | H. Breitenfellner | Panoptic segmentation |  | Started
2020-10-05 |  | BA | YoloV3 vs. YoloV4 auf Xilinx | AW/ML | F. Scherer | Arbeit in Kaiserslautern be Grimm. Netzwerkdesign |  | Started
2020-10-19 |  | BA | Hardware Aware Pruning auf OpenVino | AW | J. Westra | MobileNet OpenVino |  | Started
2020-11-03 |  | BA | Hardware Aware Slimmable Networks | AW | K. Knoth | Slimmable Networks |  | Started
2020-02-xx |  | BA | Post-Training Quantization | MW | D. Dallinger | Fast fertig |  | Started
2020-02-xx |  | MA | Pruning | ML | A. Glinserer | Fast fertig |  | Started
2020-11-xx |  | BA | Ursprüngliches Thema: Knowledge Distillation | KK | N. Alge | Neues Thema notwendig |  | Unclear
2020-11-03 |  | N/A | Power and Latency Optimization of the Xilinx ZCU102 Platform for a Pedestrian Intention Recognition Use Case | MW | M. Wuschnig | Aufgabe nach dem Reportprotokoll |  | Started
2020-11-03 |  | Sem | Tensorflow an Handy | AW | T. Kotrba | Tensorflow Lite an einem Android bringen und Netze trainieren |  | Started
NA |  |  | Power Xilinx: Generelle Powerabschätzungsmodell durch Synthetisierung erstellen | KK |  | Thema definieren |  | Unclar
|  | BA | Resourcenestimierung NVIDIA Möglichkeiten sondieren, Framework, nSight? | Martin Lechner |  | Thema definieren |  | To be defined
2020-11-03 |  | N/A | Anpassung eines Latenz- und Leistungsschätzungsmodell für ARM Prozessoren | MW | MI |  |  | Started
2020-11-18 |  | MA | 3D Convolutions an NVIDIA Hardware auswerten | Alexander Wendt |  | Thema genau mit Graz definieren |  | Open
2020-11-18 |  | BA | Edge TPU für Ampelprojekt | Alexander Wendt |  | Ausgeschrieben |  | Open
2020-11-18 |  | MA | One-shot Quantizeable Slimmable Adaptive Networks | MW | B. Schreiber | Exposé |  | Started

## Members
Abbreviation | Name
AG | Andreas Glinserer
AJ | Axel Jantsch
AM | Amid Mozelli
AW | Alexander Wendt
BH | Bernhard Haas
BS | Birgit Schreiber
CK | Christian Krieg
DD | Dominik Dallinger
HB | Helmuth Breitenfellner
JR | Julian Roth
JW | Julian Westra
KK | Karoline Knoth
LS | Lukas Steindl
MWU | Marco Wuschnig
MI | Matvey Ivanov
ML | Martin Lechner
MW | Matthias Wess
SH | Stephan Holly
TK | Thomas Kotrba
FS | Fabian Scherer

## Settings
State | Legend | Time
cancelled | WP ID: Work package sub task Id | 2020-12-17
open | Title: Sub task title
paused | Start Date: Start Date
active | End Date: Confirmed end date
completed | Description: Very short content summary
Responsible: EML member responsible or supervisor of student
Student: In case of a thesis, the student, who is active
Links: Links to sub task results
State: [not started, cancelled, running, closed]
Prio: Priority of the sub task in range [1,2,3]