## EML_Tool_WP
Compliance zu WPs CDLEML |  | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | Start Date | Est. End Date | Weight [1,5] | Progress | Description | Status | Responsible | Student | Tasks | State | Deliverable ID | Deliverable Goal | Deliverable Type | Deliverable Planned Content | Deliverable Actual Content | Priority
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  |  |  | %
[11 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
| Milestones | [9 empty] | 2020 5 8: M1.1; 2020 9 12: M2.1; 2020 11 14: M1.2; 2021 3 18: M2.2; 2021 9 24: M1.3M2.3
Deliverables
WP1.1 | Create estimations for lat, throughput, power, energy, acc, resources | [39 empty] | 51.89% | Anforderung: Modelle für 4 Platformen | Meilenstein 1.1 geschafft. Throughput nicht wichtig->auslassen | bar: 2019 10 1 to 2021 3 18
WP1.1.1 | State of the Art Latency und Power Estimation Modelle aufsetzen | [36 empty] | 2020-09-01 | 2020-10-30 |  | 100% | Setup Neural Power latency and power estimation model | Finished | MWU |  |  | completed | D1.1.1 | State of the art estimations implementation | Publication | [x] included in the publication of ANNETTE | * ANNETTE Paper: 20201224_ANETTE_IEEEAccess
| Neural Power aufsetzen mit Modell von NCS2 | [38 empty] | 2 | 100% | Modell implementieren in beliebiger Umgebung; NeuralPower übertragbar machen (andere Umgebung?); Estimatorschnittstelle implementieren; ein Modell trainieren (Xavier, NCS2…) Demonstration der Latenzabschätzung eines Netzes; Output: Latenz | -Aufgabe wird aufgelassen, weil die Ergebnisse nicht gut sind. Schlussfolgerung: Unsere Methoden sind besser | MWU |  | [x] NCS2 messdaten modellieren [-] Xilinxdaten modellieren [-] Graphikkarte Siemensserver modellieren [-] Manual schreiben [-] Am Server aufsetzen | bar: 2020 9 12 to 2020 10 13
WP1.1.2 | Latency Estimator Blackthorn (NVIDIA) | [36 empty] | 2019-10-01 | 2021-09-30 |  | 81.11% | Model based latency estimator method | Wie weit seid ihr? Wollen wir alle diese Plattformen machen? | ML | ML |  | active | D1.1.2 | Estimation model for Embedded (Nvidia) Platforms through Blackthorn | Repository, Publication | [] Publication [x] Estimation Models NVIDIA Jetson Nano [x] Estimation Models NVIDIA TX2 [] Estimation Models NVIDIA Xavier [] (ME) Repository on Github (Open source) | * Model for Nano, TX2 * Publication acceptance expected until 2021-09-30 | 1
| Martins latency estimator mit Modell von Xavier erstellen | [38 empty] | 2 | 50% |  | *Modellstruktur fertig. Übertragung auf Xavier, Messungen | ML |  | [] Messen [] Modell erstellen [] Modell übertragen [] Publikation akzeptiert | bar: 2020 12 15 to 2021 6 21
| Martins latency estimator mit Modell von Nano erstellen | [38 empty] | 5 | 90% | Modell implementieren in beliebiger Umgebung; NeuralPower übertragbar machen (andere Umgebung?); Estimatorschnittstelle implementieren; ein Modell trainieren (Xavier, NCS2…) Demonstration der Latenzabschätzung eines Netzes; | *3 Layertypen fehlen | ML |  | [] 3 Layertypen neu hinzufügen, Depth Separable Convolutions +2 [] Code aufräumen 10.12.2020->Feb. [] In Repository stellen |  |  |  |  | * Funktionierende Version auf NVIDIA-Plattformen | bar: 2020 9 12 to 2021 2 17
| Martins latency estimator mit Modell von TX2 erstellen | [38 empty] | 2 | 90% | Modell implementieren in beliebiger Umgebung; NeuralPower übertragbar machen (andere Umgebung?); Estimatorschnittstelle implementieren; ein Modell trainieren (Xavier, NCS2…) Demonstration der Latenzabschätzung eines Netzes; | *3 Layertypen fehlen | ML |  | [] 3 Layertypen neu hinzufügen [] Code aufräumen [] In Repo stellen | bar: 2020 9 12 to 2021 2 17
WP1.1.3 | Latency Estimator ANETTE (Intel, ARM, Xilinx) | [36 empty] | 2019-10-01 | 2021-09-30 |  | 85.45% | Statistic and model based latency estimator method | Wie weit bis du da? | MW | MW |  | active | D1.1.3 | Estimator method ANETTE for Latency (Intel, ARM, Xilinx) | Repository, Publication | [x] Publication of ANNETTE [x] Prediction Models of NCS2 Platform [x] Prediction Models of Xilinx Platform [] Prediction Models of ARMNN Example Platform [x] (ME) Open Source Repository for Latency Estimation | * NCS2, Xilinx ZCU102 Models fertig * Github: https://github.com/embedded-machine-learning/annette * ARMNN erstimated until 2021-09-30 | 1
| Latency Intel: ANETTE aufsetzen mit Modell von NUC erstellen | [38 empty] | 0 | 30% |  |  | MW | [6 empty] | ## ARMNN bis Ende September schaffbar | bar: 2021 1 16
| Latency Xilinx: ANETTE aufsetzen mit Modell von Xilinx ZCU102 + spezielle IP erstellen | [38 empty] | 5 | 100% |  | Xilinx ZCU102, Xilinx 4096 laufen | MW |  | [x] Schnittstelle erstellen, code cleaning | bar: 2020 9 12 to 2020 12 15
| Latency Xilinx: ANETTE aufsetzen mit Modell von Xilinx mit Ausbaustufen der IP erweitern | [38 empty] | 0 |  |  | Nicht so wichtig. Ein Xilinx reicht im Moment
| Latency Intel: ANETTE latency mit Modell von NCS2 erstellen | [38 empty] | 4 | 100% | Modell implementieren in beliebiger Umgebung; NeuralPower übertragbar machen (andere Umgebung?); Estimatorschnittstelle implementieren; ein Modell trainieren (Xavier, NCS2…) Demonstration der Latenzabschätzung eines Netzes; Size 1, sync modus | Fertig für sync modus, size 1. Schnittstelle nach außen offen | MW |  | [x] Github code online stellen. OK von SIE und ME [x] Modelle von NCS2, Xilinx auf dem Laufwerk | bar: 2020 9 12 to 2020 12 15
| Latency ARM: ANETTE auf Raspberry PI aufsetzen | [38 empty] | 2 | 20% |  | Openvino läuft auf ARM. Es sollte gleich funktionieren | MW |  | [] ARM Modell erstellen [] Modell ARM am Laufwerk | bar: 2021 1 16 to 2021 3 18
WP1.1.4 | Power Estimator through Christian's Model | [36 empty] | 2020-08-01 | 2020-10-30 |  | 0% |  |  | CK |  |  | open | D1.1.4 | Accurate power estimation method for power-aware optimization applications | Repository, Publication | [] Estimation Model Xilinx [] Comparison Performance to ANETTE [] Publication about this method [] Repository with user friendly execution code
| Power Xilinx: Generelle Powerabschätzungsmodell durch Synthetisierung erstellen | [38 empty] | 5 | 0% | Leistungsabschätzung mittels Abbildung der Netzwerk-Charakteristika auf die Plattform-Charakteristika |  | CK | bar: 2021 5 20 to 2021 9 24
WP1.1.5 | Power Estimator through ANNETTE | [36 empty] | 2020-11-11 | 2021-08-31 |  | 6.25% | Power estimation through the estimator ANNETTE |  | CK | NA |  | active | D1.1.5 | Automated characterization of hardware platforms for power based on ANNETTE | Database, repository | [] Completed power measurement environment [] Automated platform characterization for a platform | * ANNETTE Estimation of NCS2 and Edge TPU until 2021-09-30 | 2
| Power Xilinx: Powerschätzung von ANETTE auf Xilinx erweitern? | [38 empty] | 5 | 10% | Setup Messungen von WP1.3.6, Charaktärisierung der HW durch WP1.2.1. * Nachher andere * Messaufbau, allg. charactärisierungsflow (automatisiert).Plattformen, Gridsearch Plattform Datenbank, unterschiedlichen Datenbank |  | CK | NA | [] Modelle definieren |  |  |  |  | # Modell aufsetzen bis September, für NCS2 und Edge TPU bis Mai | bar: 2020 11 14 to 2021 4 19
| Power ARM: Powerestimation Raspberry PI | [38 empty] | 3 | 0% | ANETTE auf Raspberry PI erweitern. Studentenarbeit dafür verwenden | Nicht gestartet | MW
WP1.1.6 | Estimation of On-Chip Resources | [36 empty] | 2021-10-01 |  |  | 0% | Estimate resources like memory usage |  | ML |  |  | open |  |  |  |  | * Will be considered in year 3 | 3
| Resourcenestimierung NVIDIA Möglichkeiten sondieren | [38 empty] | 2 | 0% | Seminararbeit für Literatursuche. Praktische Studentenarbeit für die Ausführung. Untersuchung Memoryusage, Bandwidth, Verkehr zwischen Prozessor und DRAM. Wie kann das Ressourcenprofil ändern durch Parameterisierung. NVIDIA-Plattformen. nSight verwenden. Frage: Welches Netz würde für eine bestimmte HW die Resourcen maximal ausnutzen? | Nicht gestartet | ML |  | [] Studentenarbeit ausschreiben [] Platform mit den besten Tools auswählen |  |  |  |  | ## Im Jahr 3 berücksichtigen | bar: 2020 10 13 to 2021 4 19
[35 empty] | * | * | *
WP1.2 | Optimize HW Dependent Settings | [39 empty] | 40.69% | Anforderung: HW Optimizations für 4 Plattformen | *NVIDIA Nano und welche noch? NCS2 wäre naheliegend. Meilenstein 1.2 50% geschafft | bar: 2020 4 7 to 2021 6 21
WP1.2.1 | NVIDIA Platform Profiling (Jetson, TC2, Xavier) | [36 empty] | 2020-03-01 | 2021-03-31 |  | 41.11% | HW settings profiling of NVIDIA Xavier, Jetson Nano (Bachelor thesis) and TX2 |  | AM |  |  | active | D1.2.1 | Latency, power and energy profiling of HW options of NVIDIA Jetson Nano, Xavier, TX2 | Bachelor thesis, Publication, Documentation | [] (ME) For each device and SSD-MobileNetV2, characterzation Batchsizes 1-4, variation of possible HW options: GPU frequency, definition of settings for min. latency, min power and min energy [] Analysis of Jetson, TX2, Xavier [] (ME) Analysis of power peaks to prevent overheating [] (ME) HW configurator script in EML Github to select mode [x] Publikation | * Pub: https://ieeexplore.ieee.org/abstract/document/9290876 | 1
| NVIDIA Jetson Nano Hardware Profiling durchführen | [38 empty] | 4 | 80% | Layerstruktur. Im synchronen Modus nur. Im async geht das nicht. Zusatzmessungen Jetson Nano - Batchsize 1-4, weil sie mit einem Netz mehrere Sensorinputs gleichzeitig anschauen, Synchronbilder - Powerminimierung bzw. Powerkontrolle, weil es bei Xavier öfters passiert ist, dass der 100W Netzteil überlastet wird und das Gerät thermisch eingeht. Stresstests wären hier interessant für die Geräte bzw. wie man so einen Zustand vermeiden kann. - Für die Messungen soll ein SSD-MobileNetV2 verwendet werden |  | AM |  | [] Software von SH anpassen und auf dem letzten Stand bringen [] Jetson Nano an Matveys Setup bringen [] Messungen mit SSD-MobileNetV2 durchführen mit Matveys Setup [] Bericht mit notwendigen Messungen drinnen (Paper mit Zusatzmessungen) [] Anwendung der Messdaten in einem Estimator |  |  |  |  | [] For each device, characterzation Batchsizes 1-4, variation of possible HW options e.g. GPU frequency, definition of settings for min. latency, min power and min energy # Bis september fertig stellen | bar: 2020 9 12; 2020 11 14 to 2021 5 20
| NVIDIA Jetson Nano Optimierungsscripts erstellen | [38 empty] | 1 | 50% | Scripts implementieren, wo man Einstellungen für min Latency, min Power oder min Energy einstellen kann |  | AM |  | [] Jetson Nano Code automatisieren, eventuell mit OpenVino als Vorbild | bar: 2020 11 14 to 2021 5 20
| NVIDIA TX2 Hardware Profiling durchführen | [38 empty] | 2 | 0% | Dieselbe Messungen wir bei Nano | Nicht gestartet | AM | bar: 2021 1 16 to 2021 5 20
| NVIDIA Xavier Hardware Profiling durchführen | [38 empty] | 2 | 0% | * Dieselbe Messungen wir bei Nano * Neue Messsoftware für Xavier. Powerestimator https://jetson-tools.nvidia.com/ | Nicht gestartet | AM | bar: 2021 3 18 to 2021 5 20
WP1.2.2 | ARM Platform Profiling (Rasp. Pi 4) | [36 empty] | 2020-11-01 | 2021-02-28 |  | 46% | HW settings profiling of Raspberry Pi |  | MI |  |  | active | D1.2.2 | Performance and latency characterization of the ARM processor of a Raspberry PI as well as devloping tools for measurement execution | Repository, Document | [x] Guide how to setup ArmNN and TFLite for 32 and 64 bit of a Raspberry Pi 4 (32/64 Bit) [] Optimal settings for min. latency, min. power and min. energy found and documented [] Table with latency comparison of ArmNN and TFLite 32/64 Bit with inference with an ordinary accelerator [] (ME) Githubrepo with measurement and configuration scripts for ArmNN |  | 2
| ARM (Raspberry) HW Optimierungen untersuchen | [38 empty] | 4 | 50% | Settings für CPU -> Latenz, Power und Energy |  | MI | [6 empty] | # Nicht prio, Ziel 30.9 | bar: 2020 10 13
| ARM HW Optimierungen als Script implementieren | [38 empty] | 1 | 30% |  |  | MI
WP1.2.3 | Xilinx Rlatform Profiling (ZCU102) | [36 empty] | 2020-11-01 | 2021-05-31 |  | 6.667% | HW settings profiling of Xilinx ZCU102 |  | MWU |  |  | active | D1.2.3 | Understanding of how to adapt Xilinx images for certain network architectures | Document | [] Documented analysis how many needed kernels, share of FPGA used, consequences of consumes power, tradeoff between speedup and power [] Optimal settings for min. latency, min. power and min. energy found and documented [] Execution scripts in repository |  | 1
| Xilinx HW Optimerungensoptionen profilen | [38 empty] | 2 | 20% | Größe systosischen Array, Puffer, DSP untersuchen. Performancevariation von Arraytypen. Latencyestimation und Powerestimation darauf anzuwenden. |  | MWU |  | [] Neues Latenzmessungssoftware installieren [] AW: Usecase für Xilinx erstellen vom Ampelsystem. |  |  |  |  | # realistisch 30.11 | bar: 2020 11 14 to 2021 4 19
| Xilinx HW Optimierungen als Script implementieren | [38 empty] | 4 | 0% |  |  | MWU | bar: 2021 2 17 to 2021 5 20
WP1.2.4 | Intel Platform Profiling (NUC, NCS2) | [36 empty] | 2019-10-01 | 2020-03-31 |  | 60% | HW settings profiling of Intel NCS2 and CPU through OpenVino |  | MI |  |  | active | D1.2.4 | Latency, power and energy profiling of HW options of Intel NCS2 and Intel CPU | Document, thesis | [] Evaluation of stick sync vs. async mode and other settings of NCS2 as part of thesis MW [] Execution and configuration scripts in Scripts-and-Guides repository [x] Results included in ANNETTE D1.1.3 |  | 1
| OpenVino CPU Hardwareoptimierung untersuchen | [38 empty] | 4 | 10% | Unterschied GPU/CPU am NUC Performace, Auslastung der Cores. | Bachelorarbeit ausschreiben für Latenz und Power und Energiemessungen? | AW |  | [] Student für die Arbeit finden
| OpenVino Hardwareoptimierung Implementierung von Scripts auf NUC and NCS2 | [38 empty] | 1 | 100% | Scripts implementieren, wo man Einstellungen für min Latency, min Power oder min Energy einstellen kann |  |  |  | [] Scripts in scripts-and-guides |  |  |  |  | Wird bis 25.5 fertig
| NCS2 Hardwareoptimierungsoptionen untersuchen | [38 empty] | 4 | 100% | Settings für min Latenz, Power und Energy. Modus max. power how to use. Possiblity for syncronous inference without preprocessing. NCS2 limited through USB connector. Sync vs. asyncronous mode. Recommendation from Intel |  | MI |  | [] Doku Matvey fertig | bar: 2020 9 12 to 2020 10 13
WP1.2.5 | Google Platform Profiling (Edge TPU) | [36 empty] | 2021-03-18 | 2021-05-30 |  | 3.75% |  |  | CK | NA |  | active | D1.2.5 | Latency, power and energy profiling of HW options of Edge TPU | Document, Repo | [] Table of impact of hardware settings on latency, power and energy consumption [] Description of settings for min. latency, min. power or min. energy [] Scripts for setting optimizations in the hardware |  | 2
| Edge TPU Hardwareoptimierung durchführen | [38 empty] | 3 | 5% | Create a table of all HW settings and their affect on latency, power and energy | Started | CK | NA | [5 empty] | # 25.5 fertig | bar: 2021 3 18 to 2021 5 20
| Integration of Latency, Power and Energy settings in execution scripts | [38 empty] | 1 | 0% | bar: 2021 6 21
WP1.3 | Map Models of hardware | [39 empty] | 55.7% | Anforderung: Optimierungsstruktur für 4 Plattformen | bar: 2021 1 16 to 2021 9 24
WP1.3.1 | Common Interface Inference on all Platforms | [39 empty] | 80% | Common software interfaces for devices |  | AW |  |  | active |  | Common interface to hardware to create independence between platform specific settings and cross-hardware comparions | repository | [] Common exchange format for inference [] Common exchange format for estimators [x] Common Inference execution scripts for platforms [x] Demonstration on OpenVino and NVIDIA | * Scripts for each hardware in https://github.com/embedded-machine-learning/scripts-and-guides/tree/main/scripts/hardwaremodules | 2
| EML-Process: Gemeinsame Estimator- und Inferenzschnittstelle erstellen | [38 empty] | 2 | 80% | Das Inferenzinterface erweitern (extends) für notwendige Inputs für die Estimators; Welche Files wo in welches Format abgelegt werden, um vom Programm gefunden zu werden; Ort und Formats des Reports festlegen. WICHTIG: Diese Schnittstelle soll gleich sein wie die Schnittstelle zur echten HW | - Parser von Matthias Format vorhanden - Master: Datensatz in Matthias Format | AW |  | [] Inputformate von Martin interpretieren [x] Klären wie wir jobs nicht parallel ausführen (eventuell ohne Taskspooler) [] Doku vervollständigen [] Estimatorschnittstelle |  |  |  |  | # bis 25.5 | bar: 2020 7 10 to 2020 8 11; 2020 10 13 to 2021 3 18
| EML-Process: Startscript/Pythonschnittstelle für Inferenz an Hardwareumgebungen erstellen | [38 empty] | 2 | 80% | Standardisierte Scripts für das Ausführen der Inferenz schreiben: Inferenz mit Bericht erhalten, definieren wo es abgelegt werden soll, welches Format. |  | AW |  | [x] Infos und Scripts von Matthias und Matvey bekomme [x] Matvey NUC Openvino installieren [] Doku | bar: 2020 11 14 to 2021 5 20
WP1.3.2 | Common Network Inference Possible on NVIDIA | [36 empty] | 2020-03-01 | 2020-03-31 |  | 80% | Inference on Nano, TX2 and Xavier |  | AM |  |  | active | D1.3.2 | Inference NVIDIA: Out of the box inference with defined networks with or without tensor-rt | Document, repository | [] Guides in Github for setup of system in HW [] Scripts for inference and evaluation in Github [] Nano, TX2, Xavier environment completed [] 1x Obj. Detection Inference with tensor-rt: YoloV4 (Bck YoloV3), [] Inference trt for Object Detection API 2.0 [] 1x segmentation trt: DeepLabV3 |  | 1
| Inferenz NVIDIA: Inferenzmodul für alle NVIDIA Geräte erstellen für Latenz, Accuracy und Throughput und Timings erstellen | [38 empty] | 4 | 80% | Es soll Pytorch und TF ausführen können, Bericht im richtigen Format zurückgeben, wenn Daten und Modell bekannt sind. Gesammelt soll Netzlatenz, Layer und total, Throughput, Accuary oder IoU wenn Bilder verwendet werden, Zeit fürs Laden der Inferenzdaten, Gesamtinferenzzeit | Priorität! | AM | [6 empty] | bis 25.5 | bar: 2020 10 13 to 2020 11 14
| Inferenz NVIDIA: Inferenzmodul für Xavier aufsetzen mit Pytorch und TF 2.3 | [38 empty] | 1 | 80% | Images herunterladen und aufsetzen, TF und Pytorch letzte Versionen. Inferenzmodul mit Bericht notwendig | Priorität! *Dockerimages noch offen *OpenCV auf Xavier *trt converter läuft noch nicht wegen Versionskonflikte | AM |  | [] Tests der Images [x] Xavier am Router hängen [] TF2-Saved_Model + h5-Modelle zu tensorrt konvertieren [] Inferenz mit tensorrt und Bilder | bar: 2020 10 13 to 2020 11 14
| Inferenz NVIDIA: Inferenzmodul für TX2 aufsetzen mit Pytorch und TF 2.3 | [38 empty] | 1 | 80% | Images herunterladen und aufsetzen, TF und Pytorch letzte Versionen. Inferenzmodul mit Bericht notwendig | Priorität! | AM | bar: 2020 11 14
| Inferenz NVIDIA: Inferenzmodul für Nano aufsetzen mit Pytorch und TF 2.3 | [38 empty] | 1 | 80% | Images herunterladen und aufsetzen, TF und Pytorch letzte Versionen. Inferenzmodul mit Bericht notwendig | Priorität! | AM | bar: 2020 11 14
| Inferenz NVIDIA: Standardisierte Startscripts für NVIDIA Containers/Umgebungen erstellen | [38 empty] | 1 | 80% | Standardisierte Scripts für das Ausführen der Inferenz schreiben: Inferenz mit Bericht erhalten, definieren wo es abgelegt werden soll, welches Format |  | AM |  | [] Dockerscript erstellen | bar: 2020 10 13 to 2020 11 14
WP1.3.3 | Common Network Inference Possible on Intel | [36 empty] | 2019-10-01 | 2021-01-31 |  | 91.25% | Inference on NUC and NCS2 |  | MI |  |  | active | D1.3.3 | Inference Intel: Out of the box inference with defined networks with or without OpenVino | Document, repository | [] Guides in Github for setup of system in HW [] Scripts for inference and evaluation in Github [] NUC, NCS2 environment completed [] 1x Obj. Detection, Openvino, YoloV4 (Bck YoloV3) [] 1x segmentation, Openvino, DeepLabV3 [] Object Detection API 2.0 SSD-MobileNetV2 |  | 1
| Inferenz Intel: Inferenzmodul für alle OpenVinogeräte erstellen | [38 empty] | 4 | 100% | Es soll Pytorch und TF ausführen können, Bericht im richtigen Format zurückgeben, wenn Daten und Modell bekannt sind. Gesammelt soll Netzlatenz, Layer und total, Throughput, Accuary oder IoU wenn Bilder verwendet werden, Zeit fürs Laden der Inferenzdaten, Gesamtinferenzzeit | Deeplab, ResNet geht | MW | [6 empty] | # halben Modell von BH hat funktioniert, inputresolution halbiert. # bis 25.5 | bar: 2020 10 13 to 2020 12 15
| Inferenz Intel: Inferenzstart Script für Openvino erstellen | [38 empty] | 1 | 30% |  | Priorität! | AW |  | [] Mit einem Netz testen | bar: 2020 10 13
| Inferenz Intel: Dockerimages/Umgebungen für Intel NUC aufsetzen mit Pytorch und TF 2.3 | [38 empty] | 3 | 100% | Images herunterladen und aufsetzen, TF und Pytorch letzte Versionen. Inferenzmodul mit Bericht notwendig |  | MW | bar: 2020 10 13
WP1.3.4 | Common Network Inference Possible on ARM | [36 empty] | 2020-10-01 | 2021-02-28 |  | 10% | Inference on Raspberry Pi | Welche Hardware noch wollen wir für Inferenz? | MI |  |  | active | D1.3.4 | Inference ARM: Out of the box inference with defined networks with or without ARM-NN | Document, repository | [] Guides in Github for setup of system in HW [] Scripts for inference and evaluation in Github [] Raspberry Pi environment completed [] 1x Obj. Detection, Openvino, YoloV4 (Bck YoloV3) [] 1x segmentation, Openvino, DeepLabV3 [] TFLite Object Detection API 2.0 SSD-MobileNetV2 and InceptionResNet |  | 1
| Inferenz Edge TPU: Inferenzmodul für Google Coral Stick erstellen | [39 empty] | 0% | Es soll Pytorch und TF ausführen können, Bericht im richtigen Format zurückgeben, wenn Daten und Modell bekannt sind. Der Coral stick könnte am NUC hängen und über den NUC angesteuert werden | Pausiert |  |  | [] Edge TPU an NUC anhängen und zum Laufen zu bringen [] Inference scripts wie aus OpenVino vorbereiten |  |  |  |  | # bis 30.9 # Edge TPU separat
| Inferenz ARM Processor für TF und Pytorch ermöglichen | [38 empty] | 3 | 10% |  |  | MI |  | [] Yolov4 Inferenz möglich [] Semantic segementation Netz möglich
WP1.3.5 | Common Network Inference Possible on Xilinx | [36 empty] | 2020-10-01 | 2021-05-30 |  | 15% | Inference on Xilinx ZCU102 | Welche Hardware noch wollen wir für Inferenz? | MWU |  |  | active | D1.3.5 | Inference Xilinx: Out of the box inference with defined networks with or without Vitis-AI | Document, repository | [] Guides in Github for setup of system in HW [] Scripts for inference and evaluation in Github [] Vitis AI environment completed [] 1x Obj. Detection, Openvino, YoloV4 (Bck YoloV3) [] 1x segmentation, Openvino, DeepLabV3 |  | 1
# geschätzt bis 30.9 unsicher
| Inferenz Xilinx Processor für TF und Pytorch ermöglichen | [38 empty] | 4 | 30% | Inferenz am Xilinx machen. Vitis Software aufsetzen |  | Marco |  | [] Vitis installieren [] YoloV4 Darknet [] Semantic Segmentation Netz | bar: 2020 11 14 to 2021 1 16
| Inferenz Xilinx durch NVIDIA NVDLA Inferenz ermögichen auf einer Xilinx-Plattform | [38 empty] | 4 | 0% |  |  | MW
WP1.3.6 | Power Measurements possible for NCS2 and NVIDIA | [36 empty] | 2020-07-01 | 2020-03-31 |  | 55.23% | Allow power measurements for common HW |  | MI |  |  | active | D1.3.6 | Single networks power measurements | Script, guide | [x] Hardware power measurement setup for NCS2, Edge TPU, Xilinx and Jetson Nano [] Scripts for power measurements in Github for NCS2 and NVIDIA [] Automated measurements possible [] Measurements of latency and power at the same time possible [] Evaluation script: Varianz, Median, min, max of single layers |  | 2
| Powermessungen von NCS2 möglich | [38 empty] | 3 | 80% | Setup für Hardwaremessungen am NCS2 vorhanden | Großer Shunt 1 Ohm, Last 10 Ohm. Messung beeinflusst. USB 201 Messgerät. Problem ist USB-Anschlüsse. HW Setup fertig. | MI |  | [x] Messaufbau verfeinern [x] Löten auf ein Perfboard [x] Platz im Labor für Messungen machen [] Scripts für die Messung automatisieren |  |  |  |  | * Edge TPU Profiling auch # bis 25.5 # Postprocessing offen, sonst Messungen gleichzeitig gehen | bar: 2020 10 13 to 2020 12 15
| Softwareinterface für Powermessungen USB Geräte fertig | [38 empty] | 3 | 95% | Softwaresteuerung für die Messung. Setzen von Sampling rate, Flags, Speichern und anzeigen | Script für USB-Messungen fertig | MI |  | [] Scripts in Github [] Optional: Trigger hinzufügen fürs Staren von Messungen | bar: 2020 12 15
| Powermessungen von Jetson Nano möglich | [38 empty] | 3 | 70% |  | Stephan Hollys Messmethode. Wurde ausprobiert | MI |  | [] Messmethode [] Powermessungen während der Latenzmessung ausführen |  |  |  |  | # Scripte schreiben | bar: 2020 10 13
| Softwareinterface für Powermessungen am NVIDIA-Geräte erstellen | [38 empty] | 3 | 0%
| Powermessungen ARM Raspberry PI ermöglichen | [38 empty] | 2 | 0% |  |  | MI | bar: 2021 1 16
| Softwareinterface für Powermessungen am Raspberry PI erstellen | [38 empty] | 2 | 0% |  |  | MI | bar: 2021 1 16
| Powermessungen Xilinx ermöglichen | [38 empty] | 3 | 100% |  | Messungen an Netzen aus dem Modelzoo | MWU | bar: 2021 2 17 to 2021 3 18
| Softwareinterface für Powermessungen am Xilinx erstellen | [38 empty] | 3 | 60% |  |  | MWU |  | [] Gitrepo überprüfen. Readme hinzufügen | bar: 2021 3 18
WP1.3.7 | Demonstration of Inference on all Platforms with Common Interface | [36 empty] | 2021-03-01 | 2021-05-31 |  | 30% | Demonstration and documentation |  | AW |  |  | open | D1.3.7 | Inference of common neural networks available on all hardware | Document, validation networks | [] Overview matrix of the possibility to do inference with a certain framework on a certain hardware in the laboratory [] Guides how to setup the environments [] Guides how to do inference with a pretrained model [] Validation networks for each framework |  | 3
| Demonstration Inferenz eines SSDMobileNetV3 auf Xavier, NCS2 und ANETTE und Neural Power | [38 empty] | 2 | 30% | Ergebnis 6 Latenzen + Layerzeiten geschätzt und wirklich, 2 wirkuche, 4 geschätzte |  | AW | [6 empty] | # Bis 25.5 | bar: 2021 1 16
| Dokumentation aller erzeugten Modulen und Open Source | [38 empty] | 2 | 30% | Modul aufsetzen, Requirement.txt, Doku schreiben, Code und Doku auf Github legen |  | AW | bar: 2021 1 16
WP2.1 | Quantization | [39 empty] | 23.53% |  | Wollen wir weitere Quantisierungen anschauen? | bar: 2019 10 1 to 2020 12 15
WP2.1.1 | HW Independent Quantization on Xilinx | [36 empty] | 2020-03-01 | 2021-03-31 |  | 74% | HW independent quantization on Xilinx |  | MW | DD |  | active | D2.1.1 | Quantization of fully connected und conv layer prunable, TinyYoloV3, ResNet | Document | [] Repository with Quantization software module [] Written comprison with Vitis AI, für TinyYolo, ResNet and supported layer [] Thesis |  | 3
| Algorithmus von Dominik (Quantization) fertigstellen | [38 empty] | 4 | 80% |  | Was wird quantisiert? Weight oder alles? Mixed Quantization machen? - VITIS installiert Yolonetz zu Caffe umwandeln - Wird vor Ende fertig | DD |  | [] Vergleich mit anderen Tools machen eigenen mit anderen Quantization Tools: VITIS [] Methoden Gridsearch mit verschiedenen Parameter [x] Tiny Yolo quantizieren [] Arbeit schreiben |  |  |  |  | # 25.5 | bar: 2020 4 7 to 2021 4 19
| Dominiks Quantizationalgorithmus als Softwarepaket erstellen | [38 empty] | 1 | 50% | Interface an Algorithmus anschließen (Algoritmus als Blackbox betrachten); Algorithmus lokal demonstrieren (alles auf einem PC mit Inferenz direkt am Gerät); |  | DD |  | [] Auf Repo stellen | bar: 2020 11 14 to 2021 5 20
WP2.1.2 | Analysis of NVIDIA Native Quantization | [36 empty] | 2020-11-01 | 2021-02-28 |  | 0% | Test Tensor-RT native quantization |  | AW | KK |  | active | D2.1.2 | Effects of quantization through tensor-rt known | Document | [] Measurements of latency and accuracy of MobileNet variants w/o trt quantization all possibilities |  | 2
| NVIDIA Tensor-RT Quantizationmethoden untersuchen | [38 empty] | 2 | 0% |  |  | KK | [6 empty] | # 25.5
WP2.1.3 | Analysis of Intel Native Quantization | [36 empty] | 2020-10-01 | 2021-02-28 |  | 0% | Test OpenVino native quantization |  | AW | JW |  | active | D2.1.3 | Effect of quantization through OpenVino known | Document | [] Measurements of MobileNet variants latency and accuracy. w/o openvino quantization |  | 2
| OpenVino Quantizationmethoden untersuchen | [38 empty] | 2 | 0% |  |  | JW | [6 empty] | # Bis 25.5, sie werden immer quantisiert, Quantisierungsoptionen
WP2.1.4 | One-shot Quantizeable Slimmable Adaptive Networks on Xilinx | [36 empty] | 2020-10-01 | 2021-07-30 |  | 10% | Tradeoff between slimmable networks and quantization regarding performance loss and latency gain |  | MW | BS |  | active | D2.1.4 | Tradeoff between slimmable networks and quantization regarding performance loss and latency gain on State-of-the-Art Architectures | Repositor, Master Thesis | [] Comparison of Slimmable Networks to Depthmultiplier and pruning [] Repository to apply Methodology on other Networks |  | 2
| Mehrere Pruningmethoden testen | [38 empty] | 3 | 10% | * Once for all, one-quantizised for all, ordered dropout, Adabits, (Slimmable networks) * Optimum zwischen Pruning und Quantization. Ziel: Quantization drinnen ist und Batchnormalization integriert im Netzwerk | * Once for all, one-quantizised for all, ordered dropout, Adabits, (Slimmable networks) | [7 empty] | * Zwischenbericht schreibt sie, bis 30.9 | bar: 2020 11 14 to 2021 4 19
| Evaluieren mit unterschiedlichen Einstellungen, Pareto Opt finden | [38 empty] | 3 | 0% | Paretooptimum finden zwischen Pruning und Quantization. | bar: 2021 2 17 to 2021 7 22
| Welche Effekte mehr auf der HW | [38 empty] | 2 | 0% | bar: 2021 5 20 to 2021 9 24
WP2.2 | Pruning | [39 empty] | 36.07% |  | Welche andere Pruningmethoden wollen wir anschauen? | bar: 2019 10 1 to 2020 12 15
WP2.2.1 | HW Independent Pruning with Distiller | [36 empty] | 2020-03-01 | 2021-02-28 |  | 79.17% | HW independent pruning through distiller |  | ML | AG |  | active | D2.2.1 | Distiller derived pruning tool for simple networks ResNets for classification tasks as well as MobileNet | Thesis, Publication, Repository | [] Enhancement of Distiller pruning tool [] Performane comparison to a depth multipler at MobileNet [] ResNet classification netzwork [] Software Tool for Pytorch inputs in Repo [] Thesis |  | 3
| Algorithmus von Andreas (Pruning) fertigstellen und einschließen | [38 empty] | 5 | 85% |  | - Geht mit ResNet und MobileNet ohne trt. - Segmentation fault. Problem mit trt Slice operation nicht unterstützt - MobileNet x2 schneller, 500ms->200ms Bei ONNX Acc. Drop auf 10% - Auf ONNX umwandeln im Plan - Implementierung fertig im März - Schriftliche Arbeit Ende April | AG |  | [] Herausfinden, ob andere trt layers distiller operationen unterstützt [] ONNX Umwandlung [] Evaluierung [] Netze auf OpenVino testen [] Netze auf NVIDIA Hardware testen [] Paper schreiben [] Arbeit schreiben |  |  |  |  | bis 25.5 | bar: 2020 6 9 to 2021 5 20
| Andreas Pruningalgorithmus als Softwarepaket erstellen | [38 empty] | 1 | 50% | Interface an Algorithmus anschließen (Algoritmus als Blackbox betrachten); Algorithmus lokal demonstrieren (alles auf einem PC mit Inferenz direkt am Gerät); | Tensor-rt Umwandlung geht nicht | AW |  | [] Auf Repo stellen | bar: 2020 11 14 to 2021 5 20
WP2.2.2 | Analysis of Performance of Slimmable Networks | [36 empty] | 2020-10-01 | 2021-01-31 |  | 3.75% | Application of slimmable networks MobileNet on NVIDIA |  | MW | KK |  | active | D2.2.2 | Knowledge if slimmable networks better than MobileNet Depth multipler | Document, repository | [] Bach. Thesis: Implementation of slimmable networks on MobileNet on NVIDIA. Compare performance with depth multiplier [] Comparison of latency and acc. On device [] Repository with setup and execution scripts |  | 2
| Reproduce results on MobileNet2 | [38 empty] | 1 | 30% | Download code from repository https://github.com/JiahuiYu/slimmable_networks, let examples run locally on ICT Server, reproduce the results on the provided MobileNetV2 on ImageNet Subset, read and understand papers, research accuracy & latency measure options, Quantization methods | * ResNet-50 wurde Once-and-for-all getestet | KK |  | [] Exposé schreiben |  |  |  |  | # bis 30.11 | bar: 2020 11 14 to 2021 5 20
| Setup tensor-rt on NVIDIA Jetson Nano | [38 empty] | 1 | 0% |  |  | KK | bar: 2020 12 15 to 2021 5 20
| Experiment on MobileNetV2 | [38 empty] | 1 | 0% | On Jetson Nano |  | KK | bar: 2020 12 15 to 2021 5 20
| Experiment on Slimmed MobileNetV2 | [38 empty] | 1 | 0% | Slimmable networks, universally slimmable networks, autoslim on Jetson Nano |  | KK | bar: 2020 12 15 to 2021 5 20
| Experiment on quantized MobileNetV2 | [38 empty] | 1 | 0% |  |  | KK | bar: 2020 12 15 to 2021 5 20
| Experiment on quantized slimmed MobileNetV2 | [38 empty] | 1 | 0% |  |  | KK | bar: 2021 1 16 to 2021 5 20
| Explore how to implement latency optimization | [38 empty] | 1 | 0% | how to implement hardware aware latency optimizations for slimmable MobileNetV2 |  | KK | bar: 2021 1 16 to 2021 5 20
| Evaluate performance and latency of different nw | [38 empty] | 1 | 0% | MobileNetV2, 3 Slimmable MobileNetV2 versions, quantized and or slimmed versions |  | KK | bar: 2021 1 16 to 2021 5 20
WP2.3 | Factorization | [39 empty] | 0% |  | Hier haben wir nichts. Was machen wir? | bar: 2019 10 1 to 2020 12 15
[40 empty] | 5 | 0%
WP2.4 | Compact Design | [39 empty] | 57.33% | bar: 2020 3 6 to 2021 2 17
WP2.4.1 | Analysis of Shunt Connections for Segmentation | [36 empty] | 2020-08-01 | 2020-02-28 |  | 98.33% | Replace blocks of MobileNet with shunt connections to reduce FLOPS |  | AW | BH |  | active | D2.4.1 | Proof of concept of Knowledge distillation and shunt connections for segmentation networks. Provide an easy-to-use open-source software tool for inserting shunt connections into existing Keras networks | Publication, Master Thesis, Repository | [x] Documented results for training shunt connections using knowledge distillation both for classification and segmentation networks (Paper) [x] Inference results on NVIDIA, Xilinx and Raspberry Pi platforms [] (ME) Shunt connection algorithm Keras based in a repository [] (ME) DeeplabV3+MobileNetV3 in a Repository | * Inference results only on NVIDIA * Shunt algorithm for SSD-MobileNetV2 too | 1
| Algorithmus von Bernhard (Shuntconnections) fertigstellen | [38 empty] | 5 | 100% |  | *Imagenet dauert zu lange (10h). Eine Epoche 30min *Finetuning war erfolgreich, Knowledge Distillation abgeschlossen *Imagenet 3% geringer als vortrainiertes Netz (68% statt 71%). Preprocessing unklar. Mit der richtigen Config sollte es passen *Testbereit Anfang Dezember | BH |  | [x] GPU-Erweiterung auf 2 GPUs: Funktioniert [x] Finetuning auf Imagenet [x] Übertragen auf Deeplab [x] Inference on NVIDIA HW [-] Inference on Intel-HW [-] Inference on Raspberry PI (Only CPU) [x] Thesis written [x] Paper written and accepted |  | D2.4.1.1 |  |  | * Paper * Thesis | OK | bar: 2020 7 10 to 2021 1 16
| Bernhards Algorithmus als Softwarepaket erstellen | [38 empty] | 1 | 90% | Interface an Algorithmus anschließen (Algoritmus als Blackbox betrachten); Algorithmus lokal demonstrieren (alles auf einem PC mit Inferenz direkt am Gerät); |  | BH |  | [] Keras-Deeplab in Repo [] Shunt in Repo |  | D2.4.1.2 |  |  | * Repo online | bar: 2021 2 17 to 2021 3 18
WP2.4.2 | Evaluate Performance of SqueezeNas Models | [36 empty] | 2020-04-01 | 2021-01-31 |  | 100% | Reimplement SqueezeNAS for semantic segmentation. Compare to Deeplab |  | AM |  |  | completed | D2.4.2 | Retraining the SqueezeNAS networks on the RailSem dataset and comparing the inference results on Xavier with the results of CityScape. Compare performance to Shunt connections. Network generation for hardware | Document, Repository | [x] (ME) Report: Preprocessing of the data, Latency values on NVIDIA Xavier, IoU scores for the RailSem [x] Comparison of RailSem and CityScape on squeezenas [x] Performance and latency comparison with DeepLab [x] Github repo with experiment | *Retraining of existing Xavier models possible *New architectures not possible *Report and code: https://github.com/embedded-machine-learning/squeezenas_train; 04_Tasks\20201221_SqueezeNas_Evaluation_Amid_Mozelli
| Raildatenset für Training am Server aufbereiten | [38 empty] | 2 | 100% |  |  | AM
| Metriken und Scripts für IoU-Messungen beim Inferenz erstellen | [38 empty] | 2 | 100% | IoU berechnen. Visualisierung davon |  | AM |  | [x] Script für IoU und Visualisierung erstellen | bar: 2020 9 12 to 2020 12 15
| SqueezeNas Modelle M, L, XL mit Raildatenset trainieren | [38 empty] | 4 | 100% | 3 fertige Netzstrukturen für Xavier für Segmentationsnetze. Alle Modelle soll mit dem Raildatenset trainiert werden | *Trainieren geht *Gute IoU fehlt (15%, soll 50%-70%). Man soll mit MobileNet DeepLab trainieren *DeepLab getestet | AM |  | [x] Trainieren auf dem Server [x] Deeplab und SqueezeNas vergleichen und Bericht ergänzen [x] Alle Files auf dem Laufwerk ablegen [x] Lizenz für Repo checken [x] Code auf Github ablegen zusammen mit dem Bericht |  |  | [] Repo | bar: 2020 9 12 to 2021 1 16
WP2.4.3 | Common Backbone for semantic and instance Segmentation | [36 empty] | 2020-09-01 | 2021-04-30 |  | 27.5% | Use common MobileNet Backbone for both detection and segmentation | Welche Aufgaben stehen bevor? | AW | HB |  | active | D2.4.3 | Analysis whether a common MobileNet backbone for object detection and segmentation is faster and provides better performance as separated networks | Thesis, repository | [] (ME) Comparison acc and latency NVIDIA device of common backbone vs. separate networks [] (ME) Common backbone implementation in repo |  | 1
| Selection of state-of-the-art CNNs | [38 empty] | 2 | 100% | Networks: MobileNetV1[3], MobileNetV2[12], MobileNetV3[2] and EfficientNet[14]. | *Standardnetze mit oder ohne Optimierungen wie Shunt? | HB |  | [] Ein Netz auswählen |  |  |  |  | bis 30.9 | bar: 2020 9 12 to 2020 10 13
| Establishing of Baseline | [38 empty] | 2 | 35% | two networks for both object detection (with bounding boxes) and semantic segmentation will be built and trained separately. | * Object Detection bis auf Training fertig * https://github.com/pierluigiferrari/ssd_keras * Semantic Semgementation Netzwerk offen | HB |  | [] Kerasimplemetierung mit MobileNet auf TF2, Milestone Wirkung zu demonstrieren [] Baseline Semantic Segmenetation erstellen | bar: 2020 9 12 to 2020 10 13
| Train/test the CNN for Object Detection | [38 empty] | 2 | 30% | For this fine-tuning or training the RailSem19[15] data set will be used. |  | HB | bar: 2020 11 14 to 2020 12 15
| Freezing the encoder, train/test/ fine-tune the segmentation CNN | [38 empty] | 2 | 0% | SDD trained. Segmentation CNN head will be trained using the feature maps from the encoder. Use RailSem19. Approach of having a shared encoder for both networks. |  | HB | bar: 2021 1 16
| Simultaneous train/test both networks | [38 empty] | 2 | 0% | Unified loss function and evaluation metric will be defined. | *Könnte man hier den Panoptic Segmentation Metric verwenden = F1(Det. RQ) * mean(IoU)(Seg. Q)? | HB | bar: 2021 2 17
| Comparison and evaluation | [38 empty] | 2 | 0% | Various settings: Different network models, hyper-parameters, and number of classes. Impact on runtime and accuracy will be evaluated. Latenz und Genauigkeit im Inference lösen |  | HB |  | [] Paper aus der Arbeit machen | bar: 2021 3 18 to 2021 4 19
WP2.4.4 | Comparison of YoloV3 vs. YoloV4 on a Xilinx | [36 empty] | 2021-03-01 | 2021-08-31 |  | 0% | Comparison of YoloV3 vs. YoloV4 on a Xilinx |  | ML | FS |  | active | D2.4.4 |  | Thesis |  |  | 3
| Running YoloV3, YoloV4 and YoloV4-Scaled on Xilinx | [38 empty] | 4 | 0% | bar: 2021 3 18 to 2021 7 22
Performance comparison of YoloV3, V4 and Scaled-YoloV4 | bar: 2021 6 21 to 2021 8 23
WP2.5 | Optimization Strategy | [39 empty] | 57.12% |  | Target Plattform wäre Xilinx. Das haben wir noch nicht. Was machen wir? | bar: 2020 10 13 to 2021 9 24
WP2.5.1 | Setup Training on Server EDA01 and EDA02 | [36 empty] | 2020-05-01 | 2021-01-31 |  | 100% | Get the training server ready for Pytorch and TF2 |  | AM |  |  | Completed | D2.5.1 | Server ready for training | Document | [x] Guides on how to setup EDA01 for different environments and training [x] Environments ready: Tensorflow 2, Pytorch | * https://github.com/embedded-machine-learning/scripts-and-guides/blob/main/guides/task_spooler_manual.md
| Dockercontainer(s) mit Tensorflow 2.3 und Pytorch für EDA01 einrichten | [38 empty] | 2 | 100% | Container einrichten, Pfade für Modelle, Daten und Parameter festlegen | Statt Container venv verwenden | AM | bar: 2020 9 12
| Startscripts für Containers/Trainingsumgebungen erstellen | [38 empty] | 1 | 100% | Standardisierte Scripts fürs Steuern der Containers. Hinzufügen von Jobs zum Task Scheduler | Frage ob noch offen nachdem wir ohne Containers trainieren können? *Nur 1 GPU verwendet. Besser wäre beide GPUs. *Andreas verwendet 2 GPUs, default in Pytorch? | BH |  | [] In TF beide GPUs verwenden | bar: 2020 10 13
| Demonstration der Funktionsweise von Environments/Containers | [38 empty] | 1 | 100% | Pytorch und TF Netzwerk aussuchen, z.B. MobileNetV2, Daten zum trainieren besorgen, z.B. Imagenet, Training mit Task spooler für beide Netze sequentiell ausführen, trainierte Modelle herunterladen |  | BH | bar: 2020 11 14
| Dokumentation des Aufsetzens und Bedienung des Trainings machen | [38 empty] | 1 | 100% | Die Arbeit dokumentieren, so dass andere es reproduzieren können und anwenden können | Doku von Marco ergänzen | BH | [6 empty] | * https://github.com/embedded-machine-learning/scripts-and-guides/blob/main/guides/task_spooler_manual.md | bar: 2020 11 14
WP2.5.2 | Setup External Training on Cloud and Vienna Scientific Cluster | [36 empty] | 2020-10-01 | 2021-04-30 |  | 97.14% | Access to Amazon AWS and Vienna Scientific Cluster for training |  | AM |  |  | active | D2.5.2 | External services ready for training with our networks | Document | [x] Training possible with TF2 and Pytorch on Vienna Scientific Cluster [] Guide how to train on Microsoft Azure | * Demonstration through work of BH * Guide Scientific Cluster: \\fileserver\Projects\SoC_EML\02_Documentation\11_Tutorials\Vienna_Scientific_Cluster * Guide Azure: \\fileserver\Projects\SoC_EML\02_Documentation\11_Tutorials\Tutorial_Training_on_MS_Azure_LS.mp4 | 3
| Cloud Services vergleichen | [38 empty] | 3 | 100% | Vergleich von Amazon AWS, Microsoft unf Google bezüglich Funktion, Bedienbarkeit und Preis | Analyse abgeschlossen. Bachelorarbeit fast fertig | AW | JR | [x] Bachelorpräsentation |  |  |  |  | * Bachelorthesis | bar: 2020 11 14 to 2020 12 15
| Microsoft Azure für Training einrichten | [38 empty] | 2 | 90% | Umgebung oder Container einrichten, um auf Azure auch trainieren zu können. Ergebnis: Script, womit man wie beim EDA trainieren kann | Guide und Demonstration durch LS | AW | JW | [] Bachelorarbeit mit Guide | bar: 2021 3 18 to 2021 4 19
| Vienna Scientific Cluster für Training einrichten | [38 empty] | 2 | 100% | Zugriff auf dem Scientific Cluster. Aufgabe fertig, wenn Bernhard darauf erfolgreich trainiert hat | Training mit TF2 läuft. TF1 soll gehen, wurde aber noch nicht probiert | BH |  | [-] Doku in Github [-] Test mit TF1 | bar: 2020 9 12 to 2020 12 15
WP2.5.3 | Common Measurement Database for Hardware Inference | [39 empty] | 0% | Collect all measurements from devices and put into a database |  | AW |  |  | open | [5 empty] | 3
| TU Server für Datenbank aufsetzen | [38 empty] | 1 | 0% | Server von Daniel bekommen mit geeigneter Software |  | AW | [7 empty] | # 31.12
| Datenbankschema und Technologie auswählen | [38 empty] | 1 | 0% | z.B. PostgreSQL; Schema aus den Inferenzberichten erstellen; |  | AW
| Datenbankschnittstelle erstellen | [38 empty] | 1 | 0% | Scripts erstellen; Services für Datenbankzugriff öffnen; |  | AW
| Datenbankbetrieb demonstrieren | [38 empty] | 1 | 0% | Demonstrieren mit einem Netz, das auf Xavier Inferenz ausführt und die Metadaten + Ausführungslatenz speichert |  | AW
WP2.5.4 | Automation and Simplification of the EML Process | [36 empty] | 2021-02-01 | 2021-09-30 |  | 15% | Automate manual inference steps in the EML process |  | AW |  |  | open | [5 empty] | 3
| Softwaremodul für Schnittstelle Geräte zu Pythonsoftware schreiben | [38 empty] | 3 | 0% | Pythonmethoden für einheitliches Ausführen von Latenzmessungen an Hardware, wo IP bekannt ist und Typ. Einbindung von Protokollen und Parsern |  | AW | [6 empty] | # Inference, Training bis 25.5 # Automatische Ausführung von Optimierungsalgorithmen | bar: 2020 11 14 to 2020 12 15
| Gemeinsame Schnittstelle der Optimierungsalgorithmen definieren | [38 empty] | 3 | 0% | Herausfinden wie Inputs und Outputs aussehen; Bedarf nach Retraining und Inferenz auf einem Gerät ermitteln; Schnittstelle definieren; Implementierungstechnologie wählen (Docker?) |  | AW | bar: 2020 11 14
| Usability verbessern | [38 empty] | 2 | 60% | Visualisierung von Ergebnissen |  |  |  | [] @MI: Visualisierungstool für Graphen finden und vorbereiten | bar: 2021 2 17 to 2021 3 18
WP2.5.5 | Application: Traffic Light System | [36 empty] | 2020-03-01 | 2021-04-30 |  | 35.83% | Traffic Light System: Find best combination of HW device and network MobileNet, EfficientDet and Yolo for a pedestrian detection application |  | AW | JW |  | active | D2.5.5 | Optimal network, hardware and hardware configuration | Document | [] (TUG) Documented evaluation of EfficientDet, SSD-MobileNet and Yolo on NVIDIA, Edge TPU and NCS2 [] Optimal Network+Optimizer+Hardware as code [] Pedestrian training dataset created from official sources |  | 2
| Netzwerke, Optimierungsalgorithmen und Testhardware defineren | [38 empty] | 3 | 60% | Festlegen welche Netzwerke angeschaut werden, MobileNetV1,2,3, Auflösungen und Depth zu testen. HW festlegen: NUC, NCS2, NVIDIA alle Plattformen. Alle Netzwerke sollen in Netron darstellbar sein | * Netze noch nicht in Netron darstellbar | AW |  | [] TF2 frozen zu mmdnn konvertieren |  |  |  |  | # Bis 25.5 | bar: 2020 11 14 to 2020 12 15
| Pedestrian Datenset vorbereiten | [38 empty] | 2 | 100% | Datenset von allen Formaten in Coco oder Pascal Voc umwandeln und dann in TF Records | Datenset fertig und mit EfficientDet getestet | AW | JW | bar: 2020 11 14 to 2021 2 17
| Train MobileNet, EfficientDet, Yolo with data | [38 empty] | 1 | 50% | MobileNet V2 TF1 und TF2, EfficientDet TF2, Yolo |  | AW | bar: 2021 1 16 to 2021 4 19
| Setup test hardware | [38 empty] | 3 | 0% | Aufsetzen von NVIDIA, Edge-TPU und NUC und NCS2 |  | AW | bar: 2021 1 16 to 2021 4 19
| Inference on HW with pretrained networks | [38 empty] | 2 | 0% | Inferenz an NVIDIA, Edge-TPU, NUC und NCS2 |  | AW | bar: 2021 2 17 to 2021 5 20
| Evaluation of Networks and Performance | [38 empty] | 1 | 0% | Visualisierung, beste Kombination ermitteln | bar: 2021 4 19 to 2021 5 20
WP2.5.6 | Application: Ragweed Recognition Through a Drone | [36 empty] | 2020-08-01 | 2021-03-31 |  | 44.15% | Recognize Ragweed from a drone. Optimize Network on NVIDIA devices |  | AW | LS |  | active | D2.5.6 | Optimal network, hardware and hardware configuration | Document, Pretrained network | [] Documentation of evaluation of performance and latency of segmentation network on NVIDIA [] Trained network and data in repository [] Ragweed dataset on fileserver |  | 3
| Datensammlung | [38 empty] | 2 | 100% |  |  | LS | bar: 2020 9 12
| Daten labeln | [38 empty] | 2 | 80% | videos dabei overlapping croppen. | Alle Daten nicht gelabelt, aber es ist genug da. Jedes Format kann exportieren. Semantic segmentation offen | LS | bar: 2020 9 12
| Segmentation-Modelle trainieren | [38 empty] | 3 | 70% |  | * Daten labeln, Segmentation * Bessere Ergebnisse von Deeplab bekommen | LS |  | [] Das beste Baselinemodell finden und trainieren [] Ground Truth in Tensorboard darstellen. Segementation modell [] Daten gelabelt [] Daten auf TFRecords konvertieren [] DeeplabV3 von Bernhard baseline trainieren | bar: 2020 10 13 to 2021 4 19
| Deployment auf Embedded Devices | [38 empty] | 2 | 2% |  |  | LS | bar: 2020 12 15 to 2021 7 22
| Messungen der Leistung und des Energieverbrauchs der verschiedenen Modelle auf den verschiedenen Devices | [38 empty] | 2 | 0% |  |  | LS | bar: 2020 12 15 to 2021 8 23
| Zusammenfassung der Ergebnisse und verfassen der Diplomarbeit | [38 empty] | 2 | 0% |  | [] Bericht bis 10.5.2021 schreiben mit dem was da ist. | LS |  | [] Video von Ende der Arbeit erstellen | bar: 2021 1 16 to 2021 9 24
WP2.5.7 | Application: Minicar Demonstrator | [36 empty] | 2020-01-01 | 2021-01-31 |  | 93.33% | Minicar demonstrator for execution of detection networks on Raspberry Pi |  | MI | MI |  | active | D2.5.7 | Running demonstrator for neural networks | Repository, Model car, Bachelor Thesis | [x] Modified model car, which can be controlled by WiFI, video feed with camera image, bounding boxes with classes painted into the image by an object detection network [] Software project with scripts necessary to run the demonstrator in repository [] Written thesis about the demonstrator [x] Video with visible comparsion of networks and modi published on homepage | * Car finished | 3
| Stabil laufende Objekterkennung im Stream | [38 empty] | 4 | 100% |  | - Steuerung fertig. Neue Version verzögert die Entwicklung - Das Fahren geht gut | MI | [6 empty] | # Bis 25.5 | bar: 2020 9 12 to 2020 11 14
| Software Switch für Netzwerke/Modi | [38 empty] | 1 | 40% |  | - Flask einsetzen | MI |  | [] Flask mit Subprozessen aufsetzen | bar: 2020 10 13 to 2020 12 15
| Inferenz am RPi laufen lassen (tflite conversion + inference) + Video drehen | [38 empty] | 4 | 100% | Video drehen mit Inferenz | Object Detection braucht andere Frontend, Yolo anderes Frontend MobileNet. Inferenz mit Tflite geht (nur classification). Tflite Yolov3 Tiny geht. Langsam | MI | bar: 2020 11 14 to 2021 1 16
WP2.5.8 | Application: Tensorflow Lite Object Detection on an Android Smart Phone | [36 empty] | 2020-10-01 | 2021-02-28 |  | 56.67% | Mobile phone demonstrator for detection |  | AW | TK |  | active | D2.5.8 | Android handy with custom object detection in TF | Document, SW package | [] Guide how to setup app for TF Obj. Detection API TF2 [] App installed on mobile phone [] Coco Pretrained test network |  | 3
| Netz zu TFLite umwandeln | [38 empty] | 1 | 100% |  | - SSD-MobileNetV2 auf Coco trainiert wird | [7 empty] | # Bis 25.5 | bar: 2020 11 14
| Androidapp entwickeln | [38 empty] | 3 | 80% |  | Customized TFLite-Netz testen - Feinarbeit Processing Pipeline Image - Optisch die Oberfläche überarbeiten - Remote model download geht. TFLite-Models hochladen - Mitte april |  |  | [] Auswahlmenü fehlt, kleiner Feinschliff | bar: 2020 12 15 to 2021 4 19
| Bericht erstellen - Ausführungszeiten | [38 empty] | 1 | 0% | bar: 2021 1 16 to 2021 4 19
| Demonstrieren wie man ein vortrainiertes Netz auf das Telefon bringen kann | [38 empty] | 1 | 0% |  |  |  |  | [] AW: Netz mit annotierte Bildern erstellen | bar: 2021 2 17 to 2021 4 19
WP2.5.9 | Hyper Parameterization Optimization through a Two-Phase-Search | [36 empty] | 2020-01-01 | 2020-09-30 |  | 100% | Hyper Parameterization Optimization through a Two-Phase-Search | Completed | AW | MWU |  | completed | D2.5.9 | Find out how to speed up common SVM and RF search methods | Thesis, publication | [x] Thesis with anaylsis of search [x] Publication for IECON with results | *Thesis: 20191212_BA_Marco_Wuschning_EML_Hyperopt_closed * Publication: 20200617_Hyperparameter_Optimization_IECON * Code: see publication
| 2-Phase search algorithmus implementieren | [38 empty] | 4 | 100% | bar: 2020 1 4 to 2020 10 13
WP3 | Continuous learning | [39 empty] | NA | bar: 2020 10 13 to 2021 9 24
WP3a | On-line Object Detection | [36 empty] | 2020-03-01 | 2021-03-01 |  | 90% |  | Abgänger, schreibt noch fertig | MO | RW |  | active |  |  | Thesis, publication
WP3b | Pointcloud Registration | [36 empty] | 2020-02-01 | 2020-07-31 |  | 100% |  | Abgänger | GK | ZA |  | completed |  |  | Thesis, publication
WP3c | Self Supervised Stereo | [36 empty] | 2020-02-01 | 2020-07-31 |  | 100% |  | Abgänger | HP | KA |  | completed |  |  | Thesis, publication
WP3d | 3D Tracking Metrics | [36 empty] | 2020-01-09 | 2021-01-03 |  | 40% |  | nicht finanziert durchs CDL | GK | SL |  | active |  |  | Thesis, publication
Formatting
Task *
Workpackage w
Subtask s
Delayed d
Prolonged p
Offiziellen Milestones
M1.1: Estimation techniqe
M1.2: Optimization technique
M1.3: Design flow
MS2.1 Compression Technique Performance Comparison
MS2.2 Design Methodology
MS2.3 Design & Optimization Methodology
MS3.1 Preliminary Dataset, Baseline
MS3.2 On-line Learning System
Submilesontes
Deliverables
New Tasks
Marco: EDA-Server load measurement meathods implementation
Video: Carina: EML Presentation Video with Handy app, small presentations
EML Network: AW: Train EML network

## AG_Web_Activities
WP ID | Title | Student | Result | State
WP1.1 | Create estimations for lat, throughput, power, energy, acc, resources
WP1.1.1 | State of the Art Latency und Power Estimation Modelle aufsetzen |  | Publication | completed
WP1.1.2 | Latency Estimator Blackthorn (NVIDIA) |  | Repository, Publication | active
WP1.1.3 | Latency Estimator ANETTE (Intel, ARM, Xilinx) |  | Repository, Publication | active
WP1.1.4 | Power Estimator through Christian's Model |  | Repository, Publication | open
WP1.1.5 | Power Estimator through ANNETTE |  | Database, repository | active
WP1.1.6 | Estimation of On-Chip Resources |  |  | open
WP1.2 | Optimize HW Dependent Settings
WP1.2.1 | NVIDIA Platform Profiling (Jetson, TC2, Xavier) |  | Bachelor thesis, Publication, Documentation | active
WP1.2.2 | ARM Platform Profiling (Rasp. Pi 4) |  | Repository, Document | active
WP1.2.3 | Xilinx Rlatform Profiling (ZCU102) |  | Document | active
WP1.2.4 | Intel Platform Profiling (NUC, NCS2) |  | Document, thesis | active
WP1.2.5 | Google Platform Profiling (Edge TPU) |  | Document, Repo | active
WP1.3 | Map Models of hardware
WP1.3.1 | Common Interface Inference on all Platforms |  | repository | active
WP1.3.2 | Common Network Inference Possible on NVIDIA |  | Document, repository | active
WP1.3.3 | Common Network Inference Possible on Intel |  | Document, repository | active
WP1.3.4 | Common Network Inference Possible on ARM |  | Document, repository | active
WP1.3.5 | Common Network Inference Possible on Xilinx |  | Document, repository | active
WP1.3.6 | Power Measurements possible for NCS2 and NVIDIA |  | Script, guide | active
WP1.3.7 | Demonstration of Inference on all Platforms with Common Interface |  | Document, validation networks | open
WP2.1 | Quantization
WP2.1.1 | HW Independent Quantization on Xilinx |  | Document | active
WP2.1.2 | Analysis of NVIDIA Native Quantization |  | Document | active
WP2.1.3 | Analysis of Intel Native Quantization |  | Document | active
WP2.1.4 | One-shot Quantizeable Slimmable Adaptive Networks on Xilinx |  | Repositor, Master Thesis | active
WP2.2 | Pruning
WP2.2.1 | HW Independent Pruning with Distiller |  | Thesis, Publication, Repository | active
WP2.2.2 | Analysis of Performance of Slimmable Networks |  | Document, repository | active
WP2.3 | Factorization
WP2.4 | Compact Design
WP2.4.1 | Analysis of Shunt Connections for Segmentation |  | Publication, Master Thesis, Repository | active
WP2.4.2 | Evaluate Performance of SqueezeNas Models |  | Document, Repository | completed
WP2.4.3 | Common Backbone for semantic and instance Segmentation |  | Thesis, repository | active
WP2.4.4 | Comparison of YoloV3 vs. YoloV4 on a Xilinx |  | Thesis | active
WP2.5 | Optimization Strategy
WP2.5.1 | Setup Training on Server EDA01 and EDA02 |  | Document | Completed
WP2.5.2 | Setup External Training on Cloud and Vienna Scientific Cluster |  | Document | active
WP2.5.3 | Common Measurement Database for Hardware Inference |  |  | open
WP2.5.4 | Automation and Simplification of the EML Process |  |  | open
WP2.5.5 | Application: Traffic Light System |  | Document | active
WP2.5.6 | Application: Ragweed Recognition Through a Drone |  | Document, Pretrained network | active
WP2.5.7 | Application: Minicar Demonstrator |  | Repository, Model car, Bachelor Thesis | active
WP2.5.8 | Application: Tensorflow Lite Object Detection on an Android Smart Phone |  | Document, SW package | active
WP2.5.9 | Hyper Parameterization Optimization through a Two-Phase-Search |  | Thesis, publication | completed

## Compl_Thesis
Student | Title | Type | Location | Year | Link
Kaleab Alemayehu Kinfu | Lifelong Learning for Autonomous Vehicles: Monocular Depth Estimation | Master | TU Graz | 2020
Anam Zahra | Autonomous Vehicle Self-localization in Noisy Environments | Master | TU Graz | 2020
Andreas Glinserer | Autopruning mit Intel Distiller und Evaluation auf einem Jetson Xavier AGX | Master | TU Wien | 2021 | https://doi.org/10.34726/hss.2021.90301
Marco Wuschnig | Auswertung verschiedener Methoden der Hyperparameteroptimierung in Machine Learning | Bachelor | TU Wien | 2020 | https://publik.tuwien.ac.at/files/publik_295896.pdf
Julian Roth | Auswertung von Cloudbasierten Machine Learning Frameworks für Supervised Machine Learning | Bachelor | TU Wien | 2020 | https://publik.tuwien.ac.at/files/publik_295897.pdf
Bernhard Haas | Compressing MobileNet With Shunt Connections for NVIDIA Hardware | Master | TU Wien | 2021 | https://publik.tuwien.ac.at/files/publik_295948.pdf
Michael Opitz | Efficient Ensembles for Deep Learning | Ph.D | TU Graz | 2021
Matvey Ivanov | Embedded Machine Learning Demonstrator | Bachelor | TU Wien | 2021 | https://publik.tuwien.ac.at/files/publik_296007.pdf
Dominik Dallinger | FPGA optimized dynamic post-training quantization of TinyYoloV3 | Bachelor | TU Wien | 2021 | https://publik.tuwien.ac.at/files/publik_296008.pdf
Amid Mozelli | A Study on Confidence: an Unsupervised Multi-Agent Machine Learning Experiment | Bachelor | TU Wien | 2021
Rudolf Wörndle | Continual Domain-Incremental Learning for Object Detection | Master | TU Graz | 2020
Lukas Baischer | FPGA Based Embedded Neural Network Object Detector | Master | TU Wien | 2021 | https://doi.org/10.34726/hss.2021.69314
Lukas Steindl | Optimizing deep neural networks for efficient dronebased ragweed detection | Master | TU Wien | 2022 | https://doi.org/10.34726/hss.2022.79705
Nikolas Alge | Power Profiling of Machine Learning Accelerators using MLPerf | Bachelor | TU Wien | 2022 | https://doi.org/10.5281/zenodo.7323206

## Software
Title | Description | Link
Blackthorn | Latency Estimation Toolkit for Neural Networks (Nvidia) | https://github.com/embedded-machine-learning/blackthorn
Embedded Machine Learning Scripts and Guides | We collect scripts and guides that help us in our everyday work to setup software and frameworks. This repository is also the source of an EML Toolbox that aims to easyily implement machine learning toolchains. | https://github.com/embedded-machine-learning/scripts-and-guides
ANNETTE | Accurate Neural Network Execution Time Estimation | https://github.com/embedded-machine-learning/annette
Re-Implementation of SqueezeNas | SqueezeNAS Repository with reimplementation for a custom semenatic segementation task | https://github.com/embedded-machine-learning/squeezenas_train
EML Mobile Phone Photo Detection Application | A mobile phone application for applying detection networks on captured fotos and camera streams | https://github.com/embedded-machine-learning/eml-mobile-photo-app
Shunt Connector | Neural network compression technique called 'Shunt connection' using Keras and TensorFlow 2.x as its backend. | https://github.com/embedded-machine-learning/ShuntConnector
MobileNetV3-Segmentation-Keras | Semantic segmentation version of the MobileNetV3 architecture (source), which is inspired by the DeeplabV3 architecture. The model is implemented using Keras and TensorFlow 2.x. | https://github.com/embedded-machine-learning/MobileNetV3-Segmentation-Keras

## OpenTheses
Type | Email1 | Email2 | Link | Supervisor 1 | Supervisor 2 | Date | Title
BA | axel.jantsch@tuwien.ac.at | matthias.wess@tuwien.ac.at | https://tiss.tuwien.ac.at/thesis/thesisDetails.xhtml?dswid=9078&dsrid=628&thesisId=83155 | Jantsch | Wess | 2022-11-15 | Adaptation of a Latency and Power Estimation Model for ARM Processors
BA | axel.jantsch@tuwien.ac.at | matthias.wess@tuwien.ac.at | https://tiss.tuwien.ac.at/thesis/thesisDetails.xhtml?dswid=8615&dsrid=533&thesisId=89084 | Jantsch | Wess | 2022-11-15 | Energy Efficient Adaptive Neural Networks for Embedded Hardware
DA | axel.jantsch@tuwien.ac.at | matthias.wess@tuwien.ac.at | https://tiss.tuwien.ac.at/thesis/thesisDetails.xhtml?dswid=8461&dsrid=505&thesisId=89961 | Jantsch | Wess | 2022-11-15 | Adaptive Neural Network low bit-width Quantization for image classification, object detection and segmentation targeting FPGA
DA | axel.jantsch@tuwien.ac.at | martin.lechner@tuwien.ac.at | https://tiss.tuwien.ac.at/thesis/thesisDetails.xhtml?dswid=9579&dsrid=362&thesisId=90183 | Jantsch | Lechner | 2022-11-15 | Consistent Semantic Segmentation of Video Objects
DA | axel.jantsch@tuwien.ac.at | martin.lechner@tuwien.ac.at | https://tiss.tuwien.ac.at/thesis/thesisDetails.xhtml?dswid=7234&dsrid=684&thesisId=83157 | Jantsch | Lechner | 2020-09-28 | Hardware-Aware Pruning of Neural Networks with Intel Distiller
DA | axel.jantsch@tuwien.ac.at | martin.lechner@tuwien.ac.at | https://tiss.tuwien.ac.at/thesis/thesisDetails.xhtml?dswid=2782&dsrid=203&thesisId=85720 | Jantsch | Lechner | 2022-11-15 | Optimierung von 3D Convolutions auf Embedded Hardware für autonomes Fahren
BA | axel.jantsch@tuwien.ac.at | martin.lechner@tuwien.ac.at | https://tiss.tuwien.ac.at/thesis/thesisDetails.xhtml?dswid=8201&dsrid=413&thesisId=96423 | Jantsch | Lechner | 2022-11-15 | Real-time Simultaneous Face Detection and Pose Estimation
DA | axel.jantsch@tuwien.ac.at | matthias.bittner@tuwien.ac.at | https://tiss.tuwien.ac.at/thesis/thesisDetails.xhtml?dswid=8384&dsrid=99&thesisId=98360 | Jantsch | Bittner | 2022-11-15 | Vision based workplace safety monitor in an automotive test bench
DA | axel.jantsch@tuwien.ac.at | nima.taherinejad@tuwien.ac.at | https://tiss.tuwien.ac.at/thesis/thesisDetails.xhtml?dswid=6371&dsrid=717&thesisId=37487 | Jantsch | Nima | 2016-05-19 | Designing an all-digital DLL for an open-source DDR3 controller
DA | axel.jantsch@tuwien.ac.at |  | https://tiss.tuwien.ac.at/thesis/thesisDetails.xhtml?dswid=2720&dsrid=822&thesisId=57335 | Jantsch |  | 2018-06-28 | Deep Learning with Reduced Precision Weights
DA | axel.jantsch@tuwien.ac.at |  | https://tiss.tuwien.ac.at/thesis/thesisDetails.xhtml?dswid=1203&dsrid=744&thesisId=57337 | Jantsch |  | 2018-06-28 | Embedded Deep Learning Inference with Shift-CNN
DA | axel.jantsch@tuwien.ac.at | daniel.schnoell@tuwien.ac.at | https://eml.ict.tuwien.ac.at/PublFiles/Theses/analytical_approximation_of_statistical_rounding.pdf | Jantsch | Schnöll | 2022-11-15 | Analytical Approximation of Statistical Rounding
DA | axel.jantsch@tuwien.ac.at | maximilian.goetzinger@tuwien.ac.at | https://eml.ict.tuwien.ac.at/PublFiles/Theses/EML_Master_Thesis_Monocular_Depth_Estimation_V01.pdf | Jantsch | Götzinger | 2022-11-30 | Monocular Depth Estimation using Self/Semi-Supervised Learning
DA | axel.jantsch@tuwien.ac.at | maximilian.goetzinger@tuwien.ac.at | https://eml.ict.tuwien.ac.at/PublFiles/Theses/EML_Master_Thesis_Rail_Track_Switch_Filter_V01.pdf | Jantsch | Götzinger | 2022-11-30 | Filtering of Rail-track Switches using Ensemble Learning
BA | maximilian.goetzinger@tuwien.ac.at |  | https://eml.ict.tuwien.ac.at/PublFiles/Theses/Adapting_a_Railroad_Anomaly_Detector_for_Embedded_Hardware.pdf | Götzinger |  | 2022-12-09 | Adapting a Railroad Anomaly Detector for Embedded Hardware